## Guide
Sprint Health & Flow Dashboard: Guide
Built with Jira data and Excel. All numbers in the demo are synthetic (no real company data).
TABS
Dashboard | Headline KPIs, auto-written insights and four charts.
Sprint_Metrics | Per-sprint committed vs completed, throughput, velocity, cycle time. Calculated from Jira_Data.
Forecast | Monte Carlo forecast: how many sprints until the remaining backlog is done, at your chosen confidence.
Simulation | 500 trials behind the forecast (random, recalculates with F9). No need to edit.
Jira_Data | Sample Jira export. Paste your own data here (columns A to I).
HOW TO USE WITH YOUR OWN DATA
1. Export from Jira | Filter issues > Export > CSV. Keep: Issue key, Summary, Issue Type, Status, Story point estimate, Sprint, Created, Resolved.
2. Get 'Started' dates | Jira CSVs do not include when work began. Use a Jira automation rule or the issue history to capture the date an issue first moved to In Progress.
3. Paste into Jira_Data | Match the column order in row 1 and use real dates. Columns J and K are formulas, already filled to row 500.
4. Set the sprint inputs | On Sprint_Metrics, set the first sprint start date and sprint length. Rename sprints in column A to match your Jira sprint names.
5. Press F9 | Refreshes the Monte Carlo forecast. Change the confidence level or override remaining items on the Forecast tab.
LEGEND
Blue text on yellow | Input cells you can change.
Black text | Formulas. Do not overwrite.
ASSUMPTIONS
Cycle time | Calendar days from Started to Resolved. Lead time is Created to Resolved.
Throughput / velocity | Counted in the sprint whose dates contain the Resolved date, so spillover work is credited where it finished.
Forecast method | Each trial draws 8 sprints of throughput at random from history. It assumes future pace resembles the past and that backlog items are similarly sized.
Sprint dates | Sprints are assumed to run back to back with the same length.

## Dashboard
Sprint Health & Flow Dashboard
Demo with synthetic Jira data (10 sprints). Replace the Jira_Data tab with your own export to refresh everything.
Avg velocity (pts / sprint) | Avg throughput (items / sprint) | Median cycle time (days) | 85th pct cycle time (days)
23.1 | 9 | 4 | 9
Points done ÷ committed | Velocity variability (CV) | Bug share of all issues | Open work items
93.15% | 21.64% | 21.67% | 24
What the data says
Flow: 85% of items finish within 9 days of starting. Use this as a service-level expectation when stakeholders ask how long work takes.
Predictability: the team delivers 93% of the points it commits to per sprint, and velocity varies by about 22% sprint to sprint (lower is steadier).
Quality: bugs make up 22% of all issues. Track whether this trends down as quality practices improve.
Forecast: with 24 items remaining, there is 85% confidence of finishing within 3 sprint(s) (by 30 Aug 2026).

## Sprint_Metrics
Sprint Metrics
One row per closed sprint. Everything is calculated from Jira_Data. Edit only the yellow cells.
Sprint length (days) | 14
First sprint start date | 2026-03-02
Sprint | Start | End | Committed items | Committed points | Throughput (items done) | Velocity (points done) | Points done ÷ committed | Avg cycle time (days) | Bugs resolved
Sprint 1 | 2026-03-02 | 2026-03-15 | 10 | 20 | 8 | 17 | 85% | 4 | 4
Sprint 2 | 2026-03-16 | 2026-03-29 | 11 | 21 | 11 | 18 | 85.71% | 3.9091 | 3
Sprint 3 | 2026-03-30 | 2026-04-12 | 9 | 21 | 8 | 21 | 100% | 4.625 | 2
Sprint 4 | 2026-04-13 | 2026-04-26 | 9 | 17 | 11 | 22 | 129.4% | 6.4545 | 2
Sprint 5 | 2026-04-27 | 2026-05-10 | 8 | 27 | 8 | 25 | 92.59% | 5 | 3
Sprint 6 | 2026-05-11 | 2026-05-24 | 9 | 30 | 7 | 20 | 66.67% | 6.2857 | 0
Sprint 7 | 2026-05-25 | 2026-06-07 | 9 | 19 | 9 | 22 | 115.8% | 5.5556 | 2
Sprint 8 | 2026-06-08 | 2026-06-21 | 11 | 34 | 12 | 31 | 91.18% | 5.4167 | 2
Sprint 9 | 2026-06-22 | 2026-07-05 | 9 | 34 | 7 | 23 | 67.65% | 4.4286 | 1
Sprint 10 | 2026-07-06 | 2026-07-19 | 11 | 25 | 9 | 32 | 128% | 7.8889 | 1
Average |  |  | 9.6 | 24.8 | 9 | 23.1 | 96.2% | 5.3564 | 2
Notes: 'Throughput' and 'Velocity' count items/points whose Resolved date falls inside the sprint dates, so work that spills over is credited to the sprint where it actually finished. 'Committed' counts items tagged with that sprint in Jira_Data column F.
Formulas:
Start = [End, row above]+1
End = [Start]+B3-1

## Forecast
Monte Carlo Delivery Forecast
Each of 500 trials randomly re-plays past sprint throughput to estimate how many items get done. Press F9 to re-run the simulation.
Items remaining (auto from Jira_Data) | 24
Override remaining items (optional)
Items used in forecast | 24
Confidence level | 85%
Next sprint start | 2026-07-20
Sprint length (days) | 14
Number of trials | 500
Sprints from now | Probability backlog is done | Meets confidence level? | End of that sprint
1 | 0% | No | 2026-08-02
2 | 1.4% | No | 2026-08-16
3 | 86.2% | Yes | 2026-08-30
4 | 100% | Yes | 2026-09-13
5 | 100% | Yes | 2026-09-27
6 | 100% | Yes | 2026-10-11
7 | 100% | Yes | 2026-10-25
8 | 100% | Yes | 2026-11-08
Sprints needed at chosen confidence | 3
Forecast completion date | 2026-08-30
How to read: if the table says 85% for sprint 3, then in 85 of 100 simulated futures the remaining items were finished within 3 sprints, assuming the team's pace stays like its history.
Formulas:
End of that sprint = B7+[Sprints from now]*B8-1

## Simulation
Trial | Draw S1 | Draw S2 | Draw S3 | Draw S4 | Draw S5 | Draw S6 | Draw S7 | Draw S8 | Cum 1 sprint(s) | Cum 2 sprint(s) | Cum 3 sprint(s) | Cum 4 sprint(s) | Cum 5 sprint(s) | Cum 6 sprint(s) | Cum 7 sprint(s) | Cum 8 sprint(s)
1 | 8 | 9 | 11 | 8 | 11 | 7 | 7 | 7 | 8 | 17 | 28 | 36 | 47 | 54 | 61 | 68
2 | 11 | 8 | 9 | 11 | 8 | 11 | 7 | 12 | 11 | 19 | 28 | 39 | 47 | 58 | 65 | 77
3 | 11 | 11 | 7 | 8 | 12 | 9 | 8 | 8 | 11 | 22 | 29 | 37 | 49 | 58 | 66 | 74
4 | 9 | 8 | 9 | 8 | 8 | 8 | 11 | 9 | 9 | 17 | 26 | 34 | 42 | 50 | 61 | 70
5 | 8 | 12 | 9 | 12 | 7 | 12 | 7 | 11 | 8 | 20 | 29 | 41 | 48 | 60 | 67 | 78
6 | 12 | 7 | 11 | 7 | 8 | 11 | 9 | 12 | 12 | 19 | 30 | 37 | 45 | 56 | 65 | 77
7 | 12 | 11 | 9 | 8 | 11 | 8 | 9 | 9 | 12 | 23 | 32 | 40 | 51 | 59 | 68 | 77
8 | 11 | 12 | 12 | 7 | 7 | 7 | 11 | 8 | 11 | 23 | 35 | 42 | 49 | 56 | 67 | 75
9 | 11 | 9 | 12 | 7 | 12 | 11 | 9 | 7 | 11 | 20 | 32 | 39 | 51 | 62 | 71 | 78
10 | 7 | 8 | 9 | 8 | 11 | 7 | 11 | 7 | 7 | 15 | 24 | 32 | 43 | 50 | 61 | 68
11 | 11 | 8 | 9 | 9 | 8 | 11 | 11 | 7 | 11 | 19 | 28 | 37 | 45 | 56 | 67 | 74
12 | 11 | 7 | 12 | 7 | 7 | 9 | 8 | 8 | 11 | 18 | 30 | 37 | 44 | 53 | 61 | 69
13 | 7 | 11 | 9 | 12 | 11 | 7 | 8 | 8 | 7 | 18 | 27 | 39 | 50 | 57 | 65 | 73
14 | 7 | 8 | 7 | 8 | 7 | 7 | 8 | 8 | 7 | 15 | 22 | 30 | 37 | 44 | 52 | 60
15 | 9 | 11 | 11 | 7 | 8 | 8 | 12 | 7 | 9 | 20 | 31 | 38 | 46 | 54 | 66 | 73
16 | 12 | 8 | 11 | 7 | 9 | 7 | 7 | 7 | 12 | 20 | 31 | 38 | 47 | 54 | 61 | 68
17 | 8 | 7 | 11 | 7 | 12 | 8 | 8 | 7 | 8 | 15 | 26 | 33 | 45 | 53 | 61 | 68
18 | 8 | 12 | 12 | 11 | 8 | 11 | 11 | 9 | 8 | 20 | 32 | 43 | 51 | 62 | 73 | 82
19 | 12 | 12 | 8 | 8 | 8 | 8 | 12 | 7 | 12 | 24 | 32 | 40 | 48 | 56 | 68 | 75
20 | 7 | 11 | 8 | 11 | 8 | 8 | 8 | 7 | 7 | 18 | 26 | 37 | 45 | 53 | 61 | 68
21 | 7 | 7 | 9 | 9 | 9 | 8 | 8 | 9 | 7 | 14 | 23 | 32 | 41 | 49 | 57 | 66
22 | 7 | 8 | 11 | 7 | 12 | 7 | 9 | 7 | 7 | 15 | 26 | 33 | 45 | 52 | 61 | 68
23 | 8 | 9 | 9 | 9 | 7 | 8 | 7 | 7 | 8 | 17 | 26 | 35 | 42 | 50 | 57 | 64
24 | 8 | 12 | 11 | 12 | 11 | 8 | 7 | 8 | 8 | 20 | 31 | 43 | 54 | 62 | 69 | 77
25 | 11 | 7 | 11 | 8 | 7 | 8 | 12 | 11 | 11 | 18 | 29 | 37 | 44 | 52 | 64 | 75
26 | 8 | 8 | 7 | 8 | 8 | 9 | 9 | 9 | 8 | 16 | 23 | 31 | 39 | 48 | 57 | 66
27 | 12 | 8 | 7 | 7 | 11 | 7 | 9 | 8 | 12 | 20 | 27 | 34 | 45 | 52 | 61 | 69
28 | 8 | 12 | 8 | 8 | 11 | 11 | 8 | 9 | 8 | 20 | 28 | 36 | 47 | 58 | 66 | 75
29 | 12 | 9 | 8 | 12 | 8 | 8 | 7 | 11 | 12 | 21 | 29 | 41 | 49 | 57 | 64 | 75
30 | 7 | 8 | 12 | 8 | 8 | 8 | 8 | 9 | 7 | 15 | 27 | 35 | 43 | 51 | 59 | 68
31 | 7 | 9 | 8 | 9 | 9 | 8 | 12 | 12 | 7 | 16 | 24 | 33 | 42 | 50 | 62 | 74
32 | 9 | 9 | 7 | 12 | 8 | 8 | 9 | 8 | 9 | 18 | 25 | 37 | 45 | 53 | 62 | 70
33 | 12 | 8 | 8 | 12 | 7 | 9 | 8 | 9 | 12 | 20 | 28 | 40 | 47 | 56 | 64 | 73
34 | 9 | 7 | 11 | 7 | 12 | 8 | 9 | 12 | 9 | 16 | 27 | 34 | 46 | 54 | 63 | 75
35 | 7 | 12 | 8 | 8 | 7 | 8 | 9 | 11 | 7 | 19 | 27 | 35 | 42 | 50 | 59 | 70
36 | 11 | 9 | 8 | 8 | 12 | 8 | 7 | 7 | 11 | 20 | 28 | 36 | 48 | 56 | 63 | 70
37 | 7 | 8 | 11 | 8 | 11 | 8 | 12 | 8 | 7 | 15 | 26 | 34 | 45 | 53 | 65 | 73
38 | 8 | 8 | 7 | 8 | 12 | 11 | 12 | 8 | 8 | 16 | 23 | 31 | 43 | 54 | 66 | 74
39 | 9 | 7 | 9 | 7 | 8 | 8 | 8 | 8 | 9 | 16 | 25 | 32 | 40 | 48 | 56 | 64
40 | 11 | 8 | 7 | 8 | 8 | 12 | 11 | 11 | 11 | 19 | 26 | 34 | 42 | 54 | 65 | 76
41 | 8 | 8 | 8 | 9 | 7 | 8 | 11 | 8 | 8 | 16 | 24 | 33 | 40 | 48 | 59 | 67
42 | 8 | 7 | 11 | 7 | 9 | 8 | 11 | 8 | 8 | 15 | 26 | 33 | 42 | 50 | 61 | 69
43 | 8 | 7 | 12 | 7 | 8 | 8 | 8 | 12 | 8 | 15 | 27 | 34 | 42 | 50 | 58 | 70
44 | 11 | 7 | 7 | 11 | 8 | 8 | 8 | 9 | 11 | 18 | 25 | 36 | 44 | 52 | 60 | 69
45 | 7 | 8 | 7 | 12 | 9 | 7 | 7 | 8 | 7 | 15 | 22 | 34 | 43 | 50 | 57 | 65
46 | 8 | 11 | 9 | 11 | 7 | 8 | 9 | 9 | 8 | 19 | 28 | 39 | 46 | 54 | 63 | 72
47 | 11 | 12 | 9 | 8 | 8 | 8 | 9 | 8 | 11 | 23 | 32 | 40 | 48 | 56 | 65 | 73
48 | 7 | 12 | 8 | 11 | 8 | 9 | 8 | 12 | 7 | 19 | 27 | 38 | 46 | 55 | 63 | 75
49 | 11 | 7 | 11 | 12 | 8 | 8 | 7 | 8 | 11 | 18 | 29 | 41 | 49 | 57 | 64 | 72
50 | 8 | 7 | 9 | 9 | 9 | 8 | 8 | 7 | 8 | 15 | 24 | 33 | 42 | 50 | 58 | 65
51 | 9 | 8 | 9 | 8 | 11 | 7 | 11 | 7 | 9 | 17 | 26 | 34 | 45 | 52 | 63 | 70
52 | 11 | 7 | 12 | 7 | 7 | 7 | 12 | 9 | 11 | 18 | 30 | 37 | 44 | 51 | 63 | 72
53 | 9 | 8 | 7 | 9 | 8 | 8 | 12 | 8 | 9 | 17 | 24 | 33 | 41 | 49 | 61 | 69
54 | 12 | 11 | 8 | 9 | 11 | 8 | 8 | 9 | 12 | 23 | 31 | 40 | 51 | 59 | 67 | 76
55 | 8 | 7 | 11 | 11 | 9 | 7 | 9 | 9 | 8 | 15 | 26 | 37 | 46 | 53 | 62 | 71
56 | 12 | 7 | 8 | 7 | 8 | 9 | 7 | 11 | 12 | 19 | 27 | 34 | 42 | 51 | 58 | 69
57 | 8 | 7 | 9 | 11 | 9 | 8 | 8 | 8 | 8 | 15 | 24 | 35 | 44 | 52 | 60 | 68
58 | 9 | 11 | 9 | 7 | 9 | 11 | 7 | 9 | 9 | 20 | 29 | 36 | 45 | 56 | 63 | 72
59 | 11 | 8 | 9 | 7 | 7 | 8 | 8 | 9 | 11 | 19 | 28 | 35 | 42 | 50 | 58 | 67
60 | 8 | 12 | 8 | 11 | 7 | 12 | 8 | 7 | 8 | 20 | 28 | 39 | 46 | 58 | 66 | 73
61 | 8 | 7 | 11 | 8 | 11 | 8 | 8 | 8 | 8 | 15 | 26 | 34 | 45 | 53 | 61 | 69
62 | 7 | 7 | 7 | 9 | 9 | 12 | 8 | 8 | 7 | 14 | 21 | 30 | 39 | 51 | 59 | 67
63 | 8 | 12 | 12 | 8 | 8 | 8 | 7 | 12 | 8 | 20 | 32 | 40 | 48 | 56 | 63 | 75
64 | 7 | 8 | 7 | 11 | 8 | 7 | 7 | 11 | 7 | 15 | 22 | 33 | 41 | 48 | 55 | 66
65 | 8 | 12 | 9 | 9 | 7 | 12 | 12 | 9 | 8 | 20 | 29 | 38 | 45 | 57 | 69 | 78
66 | 8 | 9 | 8 | 8 | 9 | 8 | 11 | 8 | 8 | 17 | 25 | 33 | 42 | 50 | 61 | 69
67 | 9 | 7 | 12 | 8 | 9 | 8 | 8 | 8 | 9 | 16 | 28 | 36 | 45 | 53 | 61 | 69
68 | 11 | 12 | 9 | 11 | 9 | 8 | 8 | 8 | 11 | 23 | 32 | 43 | 52 | 60 | 68 | 76
69 | 12 | 9 | 7 | 9 | 9 | 8 | 8 | 7 | 12 | 21 | 28 | 37 | 46 | 54 | 62 | 69
70 | 9 | 7 | 7 | 7 | 9 | 9 | 11 | 12 | 9 | 16 | 23 | 30 | 39 | 48 | 59 | 71
71 | 8 | 8 | 7 | 7 | 9 | 8 | 8 | 7 | 8 | 16 | 23 | 30 | 39 | 47 | 55 | 62
72 | 8 | 9 | 12 | 7 | 7 | 8 | 11 | 9 | 8 | 17 | 29 | 36 | 43 | 51 | 62 | 71
73 | 8 | 7 | 7 | 11 | 7 | 12 | 9 | 7 | 8 | 15 | 22 | 33 | 40 | 52 | 61 | 68
74 | 7 | 12 | 9 | 12 | 7 | 12 | 7 | 11 | 7 | 19 | 28 | 40 | 47 | 59 | 66 | 77
75 | 8 | 7 | 8 | 11 | 12 | 8 | 7 | 8 | 8 | 15 | 23 | 34 | 46 | 54 | 61 | 69
76 | 8 | 11 | 7 | 8 | 8 | 11 | 11 | 8 | 8 | 19 | 26 | 34 | 42 | 53 | 64 | 72
77 | 12 | 8 | 11 | 7 | 7 | 7 | 7 | 8 | 12 | 20 | 31 | 38 | 45 | 52 | 59 | 67
78 | 11 | 12 | 7 | 8 | 9 | 7 | 8 | 9 | 11 | 23 | 30 | 38 | 47 | 54 | 62 | 71
79 | 9 | 11 | 7 | 12 | 7 | 12 | 11 | 8 | 9 | 20 | 27 | 39 | 46 | 58 | 69 | 77
80 | 7 | 8 | 12 | 8 | 8 | 7 | 7 | 11 | 7 | 15 | 27 | 35 | 43 | 50 | 57 | 68
81 | 8 | 8 | 9 | 8 | 9 | 9 | 8 | 12 | 8 | 16 | 25 | 33 | 42 | 51 | 59 | 71
82 | 11 | 8 | 12 | 7 | 11 | 9 | 7 | 7 | 11 | 19 | 31 | 38 | 49 | 58 | 65 | 72
83 | 8 | 11 | 7 | 9 | 11 | 7 | 9 | 11 | 8 | 19 | 26 | 35 | 46 | 53 | 62 | 73
84 | 7 | 11 | 7 | 8 | 11 | 8 | 8 | 7 | 7 | 18 | 25 | 33 | 44 | 52 | 60 | 67
85 | 7 | 11 | 11 | 7 | 8 | 8 | 7 | 9 | 7 | 18 | 29 | 36 | 44 | 52 | 59 | 68
86 | 9 | 9 | 7 | 8 | 11 | 9 | 7 | 7 | 9 | 18 | 25 | 33 | 44 | 53 | 60 | 67
87 | 7 | 8 | 9 | 9 | 9 | 7 | 12 | 8 | 7 | 15 | 24 | 33 | 42 | 49 | 61 | 69
88 | 7 | 9 | 8 | 8 | 9 | 8 | 8 | 7 | 7 | 16 | 24 | 32 | 41 | 49 | 57 | 64
89 | 9 | 11 | 8 | 8 | 9 | 8 | 8 | 12 | 9 | 20 | 28 | 36 | 45 | 53 | 61 | 73
90 | 9 | 8 | 7 | 8 | 11 | 8 | 12 | 12 | 9 | 17 | 24 | 32 | 43 | 51 | 63 | 75
91 | 8 | 8 | 12 | 8 | 9 | 8 | 7 | 9 | 8 | 16 | 28 | 36 | 45 | 53 | 60 | 69
92 | 8 | 11 | 11 | 7 | 8 | 9 | 7 | 11 | 8 | 19 | 30 | 37 | 45 | 54 | 61 | 72
93 | 7 | 12 | 8 | 7 | 11 | 7 | 7 | 7 | 7 | 19 | 27 | 34 | 45 | 52 | 59 | 66
94 | 11 | 7 | 8 | 12 | 7 | 9 | 11 | 7 | 11 | 18 | 26 | 38 | 45 | 54 | 65 | 72
95 | 11 | 9 | 8 | 8 | 8 | 9 | 9 | 9 | 11 | 20 | 28 | 36 | 44 | 53 | 62 | 71
96 | 8 | 8 | 12 | 11 | 11 | 7 | 8 | 12 | 8 | 16 | 28 | 39 | 50 | 57 | 65 | 77
97 | 9 | 12 | 9 | 12 | 11 | 11 | 8 | 7 | 9 | 21 | 30 | 42 | 53 | 64 | 72 | 79
98 | 11 | 11 | 9 | 8 | 7 | 9 | 8 | 8 | 11 | 22 | 31 | 39 | 46 | 55 | 63 | 71
99 | 8 | 8 | 7 | 8 | 8 | 9 | 11 | 8 | 8 | 16 | 23 | 31 | 39 | 48 | 59 | 67
100 | 12 | 12 | 7 | 8 | 12 | 8 | 11 | 11 | 12 | 24 | 31 | 39 | 51 | 59 | 70 | 81
101 | 8 | 8 | 9 | 8 | 8 | 7 | 12 | 9 | 8 | 16 | 25 | 33 | 41 | 48 | 60 | 69
102 | 12 | 8 | 9 | 7 | 8 | 7 | 9 | 8 | 12 | 20 | 29 | 36 | 44 | 51 | 60 | 68
103 | 11 | 7 | 8 | 9 | 11 | 8 | 8 | 11 | 11 | 18 | 26 | 35 | 46 | 54 | 62 | 73
104 | 9 | 7 | 8 | 7 | 9 | 7 | 11 | 7 | 9 | 16 | 24 | 31 | 40 | 47 | 58 | 65
105 | 7 | 8 | 8 | 7 | 12 | 7 | 9 | 8 | 7 | 15 | 23 | 30 | 42 | 49 | 58 | 66
106 | 8 | 11 | 11 | 7 | 7 | 8 | 9 | 9 | 8 | 19 | 30 | 37 | 44 | 52 | 61 | 70
107 | 11 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 11 | 18 | 26 | 34 | 42 | 50 | 58 | 67
108 | 9 | 7 | 11 | 8 | 9 | 9 | 7 | 7 | 9 | 16 | 27 | 35 | 44 | 53 | 60 | 67
109 | 7 | 9 | 11 | 7 | 9 | 8 | 8 | 8 | 7 | 16 | 27 | 34 | 43 | 51 | 59 | 67
110 | 9 | 7 | 8 | 11 | 9 | 7 | 9 | 11 | 9 | 16 | 24 | 35 | 44 | 51 | 60 | 71
111 | 11 | 9 | 9 | 9 | 12 | 8 | 8 | 9 | 11 | 20 | 29 | 38 | 50 | 58 | 66 | 75
112 | 11 | 8 | 8 | 8 | 8 | 11 | 12 | 8 | 11 | 19 | 27 | 35 | 43 | 54 | 66 | 74
113 | 7 | 7 | 9 | 12 | 8 | 7 | 9 | 8 | 7 | 14 | 23 | 35 | 43 | 50 | 59 | 67
114 | 9 | 8 | 9 | 7 | 12 | 8 | 8 | 11 | 9 | 17 | 26 | 33 | 45 | 53 | 61 | 72
115 | 9 | 9 | 8 | 7 | 9 | 8 | 8 | 11 | 9 | 18 | 26 | 33 | 42 | 50 | 58 | 69
116 | 7 | 8 | 7 | 8 | 9 | 9 | 9 | 11 | 7 | 15 | 22 | 30 | 39 | 48 | 57 | 68
117 | 8 | 11 | 9 | 8 | 11 | 11 | 9 | 8 | 8 | 19 | 28 | 36 | 47 | 58 | 67 | 75
118 | 11 | 9 | 9 | 12 | 9 | 11 | 9 | 8 | 11 | 20 | 29 | 41 | 50 | 61 | 70 | 78
119 | 8 | 9 | 12 | 8 | 9 | 8 | 8 | 11 | 8 | 17 | 29 | 37 | 46 | 54 | 62 | 73
120 | 11 | 8 | 8 | 8 | 9 | 7 | 9 | 8 | 11 | 19 | 27 | 35 | 44 | 51 | 60 | 68
121 | 7 | 9 | 12 | 8 | 11 | 8 | 11 | 11 | 7 | 16 | 28 | 36 | 47 | 55 | 66 | 77
122 | 11 | 11 | 8 | 11 | 8 | 11 | 11 | 7 | 11 | 22 | 30 | 41 | 49 | 60 | 71 | 78
123 | 11 | 8 | 9 | 11 | 9 | 8 | 8 | 7 | 11 | 19 | 28 | 39 | 48 | 56 | 64 | 71
124 | 7 | 8 | 7 | 7 | 11 | 8 | 7 | 12 | 7 | 15 | 22 | 29 | 40 | 48 | 55 | 67
125 | 8 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 8 | 15 | 23 | 31 | 39 | 47 | 55 | 64
126 | 7 | 9 | 11 | 8 | 8 | 8 | 12 | 12 | 7 | 16 | 27 | 35 | 43 | 51 | 63 | 75
127 | 9 | 9 | 7 | 8 | 12 | 9 | 9 | 12 | 9 | 18 | 25 | 33 | 45 | 54 | 63 | 75
128 | 9 | 7 | 8 | 9 | 8 | 8 | 8 | 7 | 9 | 16 | 24 | 33 | 41 | 49 | 57 | 64
129 | 7 | 9 | 11 | 12 | 8 | 7 | 12 | 9 | 7 | 16 | 27 | 39 | 47 | 54 | 66 | 75
130 | 12 | 9 | 7 | 9 | 8 | 11 | 8 | 11 | 12 | 21 | 28 | 37 | 45 | 56 | 64 | 75
131 | 9 | 7 | 7 | 9 | 7 | 8 | 7 | 8 | 9 | 16 | 23 | 32 | 39 | 47 | 54 | 62
132 | 11 | 11 | 11 | 11 | 9 | 7 | 8 | 7 | 11 | 22 | 33 | 44 | 53 | 60 | 68 | 75
133 | 11 | 7 | 12 | 11 | 9 | 7 | 8 | 11 | 11 | 18 | 30 | 41 | 50 | 57 | 65 | 76
134 | 9 | 7 | 11 | 9 | 9 | 9 | 8 | 7 | 9 | 16 | 27 | 36 | 45 | 54 | 62 | 69
135 | 8 | 12 | 8 | 8 | 9 | 12 | 7 | 11 | 8 | 20 | 28 | 36 | 45 | 57 | 64 | 75
136 | 8 | 9 | 9 | 11 | 8 | 9 | 11 | 8 | 8 | 17 | 26 | 37 | 45 | 54 | 65 | 73
137 | 7 | 9 | 9 | 8 | 7 | 9 | 11 | 8 | 7 | 16 | 25 | 33 | 40 | 49 | 60 | 68
138 | 9 | 11 | 9 | 9 | 11 | 9 | 9 | 7 | 9 | 20 | 29 | 38 | 49 | 58 | 67 | 74
139 | 8 | 8 | 7 | 8 | 7 | 8 | 11 | 9 | 8 | 16 | 23 | 31 | 38 | 46 | 57 | 66
140 | 9 | 12 | 11 | 8 | 8 | 11 | 7 | 7 | 9 | 21 | 32 | 40 | 48 | 59 | 66 | 73
141 | 9 | 7 | 8 | 9 | 9 | 8 | 8 | 8 | 9 | 16 | 24 | 33 | 42 | 50 | 58 | 66
142 | 9 | 9 | 9 | 11 | 9 | 8 | 11 | 12 | 9 | 18 | 27 | 38 | 47 | 55 | 66 | 78
143 | 8 | 8 | 11 | 8 | 8 | 9 | 9 | 11 | 8 | 16 | 27 | 35 | 43 | 52 | 61 | 72
144 | 8 | 11 | 12 | 7 | 11 | 12 | 12 | 12 | 8 | 19 | 31 | 38 | 49 | 61 | 73 | 85
145 | 7 | 7 | 8 | 7 | 8 | 8 | 8 | 8 | 7 | 14 | 22 | 29 | 37 | 45 | 53 | 61
146 | 7 | 7 | 7 | 11 | 8 | 7 | 12 | 8 | 7 | 14 | 21 | 32 | 40 | 47 | 59 | 67
147 | 9 | 11 | 8 | 11 | 11 | 11 | 9 | 9 | 9 | 20 | 28 | 39 | 50 | 61 | 70 | 79
148 | 7 | 11 | 9 | 8 | 11 | 9 | 8 | 9 | 7 | 18 | 27 | 35 | 46 | 55 | 63 | 72
149 | 8 | 11 | 11 | 11 | 12 | 8 | 8 | 8 | 8 | 19 | 30 | 41 | 53 | 61 | 69 | 77
150 | 8 | 8 | 7 | 7 | 8 | 7 | 9 | 11 | 8 | 16 | 23 | 30 | 38 | 45 | 54 | 65
151 | 9 | 9 | 7 | 8 | 11 | 8 | 11 | 9 | 9 | 18 | 25 | 33 | 44 | 52 | 63 | 72
152 | 7 | 8 | 12 | 7 | 9 | 7 | 11 | 9 | 7 | 15 | 27 | 34 | 43 | 50 | 61 | 70
153 | 8 | 9 | 9 | 11 | 8 | 7 | 8 | 9 | 8 | 17 | 26 | 37 | 45 | 52 | 60 | 69
154 | 7 | 11 | 12 | 7 | 8 | 11 | 9 | 11 | 7 | 18 | 30 | 37 | 45 | 56 | 65 | 76
155 | 12 | 9 | 7 | 8 | 7 | 7 | 12 | 9 | 12 | 21 | 28 | 36 | 43 | 50 | 62 | 71
156 | 11 | 9 | 11 | 11 | 8 | 12 | 9 | 8 | 11 | 20 | 31 | 42 | 50 | 62 | 71 | 79
157 | 7 | 8 | 8 | 8 | 11 | 7 | 8 | 8 | 7 | 15 | 23 | 31 | 42 | 49 | 57 | 65
158 | 11 | 9 | 8 | 7 | 8 | 7 | 7 | 11 | 11 | 20 | 28 | 35 | 43 | 50 | 57 | 68
159 | 7 | 11 | 7 | 8 | 11 | 8 | 7 | 12 | 7 | 18 | 25 | 33 | 44 | 52 | 59 | 71
160 | 12 | 7 | 8 | 7 | 12 | 11 | 7 | 7 | 12 | 19 | 27 | 34 | 46 | 57 | 64 | 71
161 | 8 | 11 | 8 | 8 | 9 | 9 | 8 | 8 | 8 | 19 | 27 | 35 | 44 | 53 | 61 | 69
162 | 12 | 7 | 7 | 7 | 9 | 12 | 11 | 12 | 12 | 19 | 26 | 33 | 42 | 54 | 65 | 77
163 | 8 | 11 | 8 | 11 | 9 | 7 | 8 | 8 | 8 | 19 | 27 | 38 | 47 | 54 | 62 | 70
164 | 9 | 11 | 9 | 9 | 8 | 9 | 8 | 9 | 9 | 20 | 29 | 38 | 46 | 55 | 63 | 72
165 | 11 | 12 | 8 | 7 | 11 | 11 | 8 | 8 | 11 | 23 | 31 | 38 | 49 | 60 | 68 | 76
166 | 11 | 11 | 11 | 7 | 9 | 8 | 11 | 8 | 11 | 22 | 33 | 40 | 49 | 57 | 68 | 76
167 | 9 | 8 | 7 | 11 | 12 | 8 | 7 | 12 | 9 | 17 | 24 | 35 | 47 | 55 | 62 | 74
168 | 8 | 12 | 7 | 12 | 8 | 8 | 8 | 7 | 8 | 20 | 27 | 39 | 47 | 55 | 63 | 70
169 | 8 | 9 | 11 | 7 | 8 | 8 | 11 | 8 | 8 | 17 | 28 | 35 | 43 | 51 | 62 | 70
170 | 9 | 8 | 7 | 11 | 7 | 9 | 8 | 7 | 9 | 17 | 24 | 35 | 42 | 51 | 59 | 66
171 | 8 | 8 | 8 | 7 | 8 | 9 | 8 | 7 | 8 | 16 | 24 | 31 | 39 | 48 | 56 | 63
172 | 11 | 8 | 11 | 11 | 8 | 7 | 8 | 8 | 11 | 19 | 30 | 41 | 49 | 56 | 64 | 72
173 | 8 | 9 | 8 | 7 | 7 | 11 | 12 | 11 | 8 | 17 | 25 | 32 | 39 | 50 | 62 | 73
174 | 7 | 11 | 9 | 7 | 7 | 8 | 9 | 9 | 7 | 18 | 27 | 34 | 41 | 49 | 58 | 67
175 | 11 | 7 | 8 | 11 | 8 | 8 | 9 | 11 | 11 | 18 | 26 | 37 | 45 | 53 | 62 | 73
176 | 11 | 7 | 8 | 12 | 7 | 8 | 7 | 9 | 11 | 18 | 26 | 38 | 45 | 53 | 60 | 69
177 | 7 | 8 | 8 | 8 | 11 | 12 | 8 | 7 | 7 | 15 | 23 | 31 | 42 | 54 | 62 | 69
178 | 8 | 11 | 7 | 8 | 7 | 12 | 9 | 11 | 8 | 19 | 26 | 34 | 41 | 53 | 62 | 73
179 | 8 | 11 | 9 | 7 | 11 | 12 | 11 | 11 | 8 | 19 | 28 | 35 | 46 | 58 | 69 | 80
180 | 8 | 9 | 7 | 9 | 8 | 8 | 7 | 11 | 8 | 17 | 24 | 33 | 41 | 49 | 56 | 67
181 | 9 | 7 | 11 | 11 | 8 | 9 | 8 | 8 | 9 | 16 | 27 | 38 | 46 | 55 | 63 | 71
182 | 9 | 11 | 12 | 8 | 11 | 9 | 11 | 9 | 9 | 20 | 32 | 40 | 51 | 60 | 71 | 80
183 | 12 | 11 | 8 | 8 | 9 | 11 | 7 | 8 | 12 | 23 | 31 | 39 | 48 | 59 | 66 | 74
184 | 8 | 9 | 7 | 9 | 8 | 9 | 7 | 7 | 8 | 17 | 24 | 33 | 41 | 50 | 57 | 64
185 | 11 | 9 | 8 | 11 | 8 | 11 | 7 | 7 | 11 | 20 | 28 | 39 | 47 | 58 | 65 | 72
186 | 8 | 7 | 8 | 8 | 7 | 8 | 11 | 8 | 8 | 15 | 23 | 31 | 38 | 46 | 57 | 65
187 | 9 | 7 | 7 | 11 | 11 | 8 | 7 | 11 | 9 | 16 | 23 | 34 | 45 | 53 | 60 | 71
188 | 9 | 8 | 7 | 11 | 11 | 9 | 12 | 7 | 9 | 17 | 24 | 35 | 46 | 55 | 67 | 74
189 | 8 | 9 | 8 | 12 | 8 | 11 | 9 | 8 | 8 | 17 | 25 | 37 | 45 | 56 | 65 | 73
190 | 8 | 12 | 8 | 8 | 11 | 8 | 8 | 7 | 8 | 20 | 28 | 36 | 47 | 55 | 63 | 70
191 | 11 | 9 | 7 | 11 | 9 | 7 | 12 | 7 | 11 | 20 | 27 | 38 | 47 | 54 | 66 | 73
192 | 12 | 9 | 8 | 12 | 7 | 11 | 12 | 11 | 12 | 21 | 29 | 41 | 48 | 59 | 71 | 82
193 | 8 | 8 | 8 | 8 | 7 | 7 | 11 | 11 | 8 | 16 | 24 | 32 | 39 | 46 | 57 | 68
194 | 8 | 11 | 8 | 11 | 12 | 7 | 8 | 8 | 8 | 19 | 27 | 38 | 50 | 57 | 65 | 73
195 | 11 | 7 | 8 | 8 | 11 | 8 | 9 | 11 | 11 | 18 | 26 | 34 | 45 | 53 | 62 | 73
196 | 8 | 9 | 9 | 11 | 8 | 11 | 8 | 7 | 8 | 17 | 26 | 37 | 45 | 56 | 64 | 71
197 | 8 | 9 | 7 | 7 | 9 | 9 | 8 | 9 | 8 | 17 | 24 | 31 | 40 | 49 | 57 | 66
198 | 7 | 7 | 8 | 11 | 8 | 8 | 8 | 8 | 7 | 14 | 22 | 33 | 41 | 49 | 57 | 65
199 | 11 | 12 | 7 | 8 | 8 | 12 | 12 | 7 | 11 | 23 | 30 | 38 | 46 | 58 | 70 | 77
200 | 8 | 8 | 7 | 9 | 8 | 7 | 9 | 9 | 8 | 16 | 23 | 32 | 40 | 47 | 56 | 65
201 | 8 | 8 | 9 | 12 | 8 | 8 | 8 | 11 | 8 | 16 | 25 | 37 | 45 | 53 | 61 | 72
202 | 8 | 8 | 11 | 9 | 9 | 12 | 8 | 9 | 8 | 16 | 27 | 36 | 45 | 57 | 65 | 74
203 | 9 | 7 | 9 | 9 | 8 | 8 | 9 | 8 | 9 | 16 | 25 | 34 | 42 | 50 | 59 | 67
204 | 11 | 8 | 11 | 9 | 8 | 8 | 8 | 8 | 11 | 19 | 30 | 39 | 47 | 55 | 63 | 71
205 | 8 | 7 | 9 | 8 | 8 | 8 | 9 | 8 | 8 | 15 | 24 | 32 | 40 | 48 | 57 | 65
206 | 8 | 7 | 9 | 11 | 8 | 8 | 8 | 8 | 8 | 15 | 24 | 35 | 43 | 51 | 59 | 67
207 | 12 | 7 | 12 | 7 | 8 | 9 | 11 | 7 | 12 | 19 | 31 | 38 | 46 | 55 | 66 | 73
208 | 9 | 7 | 8 | 12 | 7 | 11 | 8 | 8 | 9 | 16 | 24 | 36 | 43 | 54 | 62 | 70
209 | 8 | 9 | 11 | 7 | 7 | 11 | 8 | 7 | 8 | 17 | 28 | 35 | 42 | 53 | 61 | 68
210 | 11 | 7 | 12 | 11 | 9 | 9 | 9 | 11 | 11 | 18 | 30 | 41 | 50 | 59 | 68 | 79
211 | 11 | 8 | 7 | 9 | 11 | 11 | 8 | 7 | 11 | 19 | 26 | 35 | 46 | 57 | 65 | 72
212 | 8 | 12 | 9 | 8 | 9 | 9 | 11 | 11 | 8 | 20 | 29 | 37 | 46 | 55 | 66 | 77
213 | 12 | 12 | 9 | 9 | 8 | 11 | 8 | 11 | 12 | 24 | 33 | 42 | 50 | 61 | 69 | 80
214 | 12 | 9 | 12 | 7 | 8 | 9 | 9 | 12 | 12 | 21 | 33 | 40 | 48 | 57 | 66 | 78
215 | 7 | 8 | 8 | 8 | 8 | 11 | 8 | 7 | 7 | 15 | 23 | 31 | 39 | 50 | 58 | 65
216 | 9 | 11 | 8 | 8 | 9 | 7 | 7 | 9 | 9 | 20 | 28 | 36 | 45 | 52 | 59 | 68
217 | 12 | 8 | 7 | 7 | 7 | 7 | 11 | 9 | 12 | 20 | 27 | 34 | 41 | 48 | 59 | 68
218 | 8 | 7 | 7 | 11 | 8 | 11 | 8 | 9 | 8 | 15 | 22 | 33 | 41 | 52 | 60 | 69
219 | 9 | 9 | 12 | 11 | 12 | 7 | 8 | 8 | 9 | 18 | 30 | 41 | 53 | 60 | 68 | 76
220 | 11 | 12 | 8 | 11 | 8 | 8 | 8 | 7 | 11 | 23 | 31 | 42 | 50 | 58 | 66 | 73
221 | 8 | 7 | 11 | 8 | 7 | 8 | 9 | 9 | 8 | 15 | 26 | 34 | 41 | 49 | 58 | 67
222 | 7 | 8 | 8 | 9 | 9 | 12 | 7 | 8 | 7 | 15 | 23 | 32 | 41 | 53 | 60 | 68
223 | 7 | 11 | 8 | 8 | 8 | 11 | 9 | 8 | 7 | 18 | 26 | 34 | 42 | 53 | 62 | 70
224 | 12 | 9 | 11 | 8 | 8 | 8 | 12 | 11 | 12 | 21 | 32 | 40 | 48 | 56 | 68 | 79
225 | 8 | 8 | 8 | 11 | 7 | 7 | 7 | 7 | 8 | 16 | 24 | 35 | 42 | 49 | 56 | 63
226 | 9 | 7 | 8 | 7 | 11 | 8 | 12 | 11 | 9 | 16 | 24 | 31 | 42 | 50 | 62 | 73
227 | 8 | 7 | 11 | 8 | 8 | 8 | 8 | 8 | 8 | 15 | 26 | 34 | 42 | 50 | 58 | 66
228 | 12 | 8 | 9 | 11 | 11 | 8 | 8 | 8 | 12 | 20 | 29 | 40 | 51 | 59 | 67 | 75
229 | 9 | 11 | 11 | 8 | 7 | 8 | 9 | 12 | 9 | 20 | 31 | 39 | 46 | 54 | 63 | 75
230 | 8 | 11 | 9 | 7 | 12 | 9 | 9 | 7 | 8 | 19 | 28 | 35 | 47 | 56 | 65 | 72
231 | 8 | 11 | 11 | 12 | 9 | 8 | 11 | 9 | 8 | 19 | 30 | 42 | 51 | 59 | 70 | 79
232 | 8 | 9 | 8 | 9 | 7 | 11 | 9 | 7 | 8 | 17 | 25 | 34 | 41 | 52 | 61 | 68
233 | 11 | 9 | 9 | 8 | 7 | 8 | 11 | 11 | 11 | 20 | 29 | 37 | 44 | 52 | 63 | 74
234 | 12 | 8 | 12 | 8 | 7 | 8 | 7 | 8 | 12 | 20 | 32 | 40 | 47 | 55 | 62 | 70
235 | 9 | 8 | 7 | 12 | 11 | 7 | 8 | 8 | 9 | 17 | 24 | 36 | 47 | 54 | 62 | 70
236 | 7 | 9 | 8 | 11 | 7 | 7 | 9 | 11 | 7 | 16 | 24 | 35 | 42 | 49 | 58 | 69
237 | 11 | 7 | 9 | 8 | 12 | 8 | 11 | 11 | 11 | 18 | 27 | 35 | 47 | 55 | 66 | 77
238 | 11 | 9 | 11 | 8 | 7 | 8 | 8 | 9 | 11 | 20 | 31 | 39 | 46 | 54 | 62 | 71
239 | 11 | 8 | 11 | 11 | 11 | 11 | 8 | 11 | 11 | 19 | 30 | 41 | 52 | 63 | 71 | 82
240 | 11 | 9 | 7 | 12 | 9 | 9 | 12 | 7 | 11 | 20 | 27 | 39 | 48 | 57 | 69 | 76
241 | 8 | 9 | 8 | 8 | 7 | 11 | 12 | 9 | 8 | 17 | 25 | 33 | 40 | 51 | 63 | 72
242 | 7 | 7 | 8 | 8 | 7 | 11 | 11 | 8 | 7 | 14 | 22 | 30 | 37 | 48 | 59 | 67
243 | 9 | 12 | 11 | 12 | 8 | 7 | 12 | 9 | 9 | 21 | 32 | 44 | 52 | 59 | 71 | 80
244 | 7 | 8 | 12 | 11 | 12 | 11 | 12 | 8 | 7 | 15 | 27 | 38 | 50 | 61 | 73 | 81
245 | 9 | 7 | 8 | 12 | 11 | 7 | 7 | 8 | 9 | 16 | 24 | 36 | 47 | 54 | 61 | 69
246 | 8 | 8 | 8 | 7 | 7 | 9 | 12 | 11 | 8 | 16 | 24 | 31 | 38 | 47 | 59 | 70
247 | 8 | 8 | 8 | 7 | 8 | 11 | 9 | 7 | 8 | 16 | 24 | 31 | 39 | 50 | 59 | 66
248 | 9 | 8 | 8 | 11 | 9 | 8 | 11 | 7 | 9 | 17 | 25 | 36 | 45 | 53 | 64 | 71
249 | 9 | 9 | 8 | 12 | 9 | 8 | 9 | 8 | 9 | 18 | 26 | 38 | 47 | 55 | 64 | 72
250 | 11 | 7 | 9 | 9 | 7 | 8 | 7 | 8 | 11 | 18 | 27 | 36 | 43 | 51 | 58 | 66
251 | 7 | 9 | 8 | 11 | 9 | 7 | 7 | 12 | 7 | 16 | 24 | 35 | 44 | 51 | 58 | 70
252 | 9 | 11 | 9 | 7 | 12 | 9 | 9 | 8 | 9 | 20 | 29 | 36 | 48 | 57 | 66 | 74
253 | 9 | 8 | 7 | 7 | 7 | 7 | 11 | 7 | 9 | 17 | 24 | 31 | 38 | 45 | 56 | 63
254 | 7 | 8 | 7 | 11 | 8 | 8 | 7 | 8 | 7 | 15 | 22 | 33 | 41 | 49 | 56 | 64
255 | 12 | 7 | 11 | 7 | 9 | 11 | 12 | 8 | 12 | 19 | 30 | 37 | 46 | 57 | 69 | 77
256 | 7 | 8 | 8 | 11 | 8 | 8 | 8 | 8 | 7 | 15 | 23 | 34 | 42 | 50 | 58 | 66
257 | 7 | 11 | 8 | 7 | 8 | 9 | 8 | 7 | 7 | 18 | 26 | 33 | 41 | 50 | 58 | 65
258 | 7 | 7 | 9 | 8 | 12 | 7 | 11 | 8 | 7 | 14 | 23 | 31 | 43 | 50 | 61 | 69
259 | 9 | 7 | 8 | 12 | 8 | 8 | 7 | 12 | 9 | 16 | 24 | 36 | 44 | 52 | 59 | 71
260 | 7 | 8 | 9 | 8 | 7 | 11 | 8 | 8 | 7 | 15 | 24 | 32 | 39 | 50 | 58 | 66
261 | 8 | 11 | 8 | 8 | 11 | 8 | 8 | 11 | 8 | 19 | 27 | 35 | 46 | 54 | 62 | 73
262 | 11 | 9 | 11 | 12 | 7 | 8 | 9 | 11 | 11 | 20 | 31 | 43 | 50 | 58 | 67 | 78
263 | 9 | 11 | 12 | 11 | 8 | 11 | 12 | 8 | 9 | 20 | 32 | 43 | 51 | 62 | 74 | 82
264 | 7 | 7 | 12 | 7 | 11 | 11 | 9 | 9 | 7 | 14 | 26 | 33 | 44 | 55 | 64 | 73
265 | 9 | 12 | 8 | 7 | 8 | 7 | 8 | 11 | 9 | 21 | 29 | 36 | 44 | 51 | 59 | 70
266 | 7 | 7 | 7 | 11 | 7 | 7 | 7 | 11 | 7 | 14 | 21 | 32 | 39 | 46 | 53 | 64
267 | 9 | 12 | 9 | 8 | 8 | 8 | 12 | 9 | 9 | 21 | 30 | 38 | 46 | 54 | 66 | 75
268 | 8 | 8 | 7 | 8 | 12 | 11 | 11 | 11 | 8 | 16 | 23 | 31 | 43 | 54 | 65 | 76
269 | 7 | 9 | 11 | 7 | 9 | 11 | 11 | 11 | 7 | 16 | 27 | 34 | 43 | 54 | 65 | 76
270 | 8 | 9 | 7 | 7 | 12 | 8 | 9 | 7 | 8 | 17 | 24 | 31 | 43 | 51 | 60 | 67
271 | 7 | 8 | 8 | 7 | 11 | 11 | 7 | 11 | 7 | 15 | 23 | 30 | 41 | 52 | 59 | 70
272 | 11 | 7 | 8 | 8 | 11 | 11 | 11 | 9 | 11 | 18 | 26 | 34 | 45 | 56 | 67 | 76
273 | 7 | 7 | 8 | 11 | 9 | 12 | 9 | 11 | 7 | 14 | 22 | 33 | 42 | 54 | 63 | 74
274 | 7 | 7 | 8 | 8 | 11 | 11 | 9 | 9 | 7 | 14 | 22 | 30 | 41 | 52 | 61 | 70
275 | 8 | 11 | 9 | 11 | 11 | 8 | 9 | 8 | 8 | 19 | 28 | 39 | 50 | 58 | 67 | 75
276 | 7 | 8 | 12 | 9 | 8 | 8 | 11 | 11 | 7 | 15 | 27 | 36 | 44 | 52 | 63 | 74
277 | 11 | 9 | 11 | 12 | 11 | 8 | 7 | 11 | 11 | 20 | 31 | 43 | 54 | 62 | 69 | 80
278 | 8 | 9 | 11 | 8 | 11 | 8 | 11 | 8 | 8 | 17 | 28 | 36 | 47 | 55 | 66 | 74
279 | 8 | 7 | 12 | 9 | 12 | 11 | 8 | 9 | 8 | 15 | 27 | 36 | 48 | 59 | 67 | 76
280 | 11 | 11 | 9 | 9 | 9 | 8 | 9 | 12 | 11 | 22 | 31 | 40 | 49 | 57 | 66 | 78
281 | 11 | 8 | 9 | 11 | 8 | 7 | 8 | 11 | 11 | 19 | 28 | 39 | 47 | 54 | 62 | 73
282 | 11 | 11 | 8 | 8 | 8 | 7 | 12 | 12 | 11 | 22 | 30 | 38 | 46 | 53 | 65 | 77
283 | 8 | 9 | 11 | 7 | 12 | 9 | 11 | 8 | 8 | 17 | 28 | 35 | 47 | 56 | 67 | 75
284 | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 9 | 12 | 24 | 32 | 40 | 48 | 56 | 64 | 73
285 | 11 | 7 | 9 | 8 | 8 | 8 | 9 | 7 | 11 | 18 | 27 | 35 | 43 | 51 | 60 | 67
286 | 7 | 9 | 7 | 8 | 9 | 9 | 9 | 7 | 7 | 16 | 23 | 31 | 40 | 49 | 58 | 65
287 | 9 | 7 | 11 | 12 | 7 | 8 | 8 | 11 | 9 | 16 | 27 | 39 | 46 | 54 | 62 | 73
288 | 12 | 12 | 8 | 8 | 11 | 9 | 8 | 7 | 12 | 24 | 32 | 40 | 51 | 60 | 68 | 75
289 | 8 | 7 | 11 | 9 | 8 | 8 | 7 | 7 | 8 | 15 | 26 | 35 | 43 | 51 | 58 | 65
290 | 8 | 8 | 7 | 8 | 7 | 11 | 9 | 8 | 8 | 16 | 23 | 31 | 38 | 49 | 58 | 66
291 | 9 | 8 | 12 | 12 | 7 | 9 | 11 | 11 | 9 | 17 | 29 | 41 | 48 | 57 | 68 | 79
292 | 8 | 8 | 12 | 7 | 11 | 11 | 8 | 7 | 8 | 16 | 28 | 35 | 46 | 57 | 65 | 72
293 | 11 | 11 | 8 | 7 | 11 | 7 | 8 | 8 | 11 | 22 | 30 | 37 | 48 | 55 | 63 | 71
294 | 8 | 9 | 12 | 12 | 9 | 11 | 12 | 7 | 8 | 17 | 29 | 41 | 50 | 61 | 73 | 80
295 | 7 | 8 | 7 | 12 | 8 | 8 | 12 | 12 | 7 | 15 | 22 | 34 | 42 | 50 | 62 | 74
296 | 9 | 7 | 8 | 11 | 11 | 11 | 7 | 11 | 9 | 16 | 24 | 35 | 46 | 57 | 64 | 75
297 | 8 | 11 | 7 | 8 | 9 | 12 | 11 | 7 | 8 | 19 | 26 | 34 | 43 | 55 | 66 | 73
298 | 7 | 8 | 7 | 11 | 7 | 8 | 9 | 7 | 7 | 15 | 22 | 33 | 40 | 48 | 57 | 64
299 | 11 | 8 | 7 | 7 | 7 | 9 | 11 | 12 | 11 | 19 | 26 | 33 | 40 | 49 | 60 | 72
300 | 7 | 8 | 7 | 9 | 9 | 7 | 12 | 7 | 7 | 15 | 22 | 31 | 40 | 47 | 59 | 66
301 | 8 | 9 | 8 | 8 | 7 | 7 | 8 | 8 | 8 | 17 | 25 | 33 | 40 | 47 | 55 | 63
302 | 12 | 9 | 7 | 9 | 8 | 11 | 9 | 9 | 12 | 21 | 28 | 37 | 45 | 56 | 65 | 74
303 | 11 | 8 | 7 | 12 | 11 | 8 | 8 | 9 | 11 | 19 | 26 | 38 | 49 | 57 | 65 | 74
304 | 11 | 8 | 8 | 8 | 9 | 7 | 7 | 8 | 11 | 19 | 27 | 35 | 44 | 51 | 58 | 66
305 | 8 | 8 | 8 | 8 | 11 | 9 | 7 | 12 | 8 | 16 | 24 | 32 | 43 | 52 | 59 | 71
306 | 7 | 12 | 9 | 7 | 7 | 7 | 11 | 11 | 7 | 19 | 28 | 35 | 42 | 49 | 60 | 71
307 | 8 | 11 | 8 | 8 | 7 | 9 | 7 | 7 | 8 | 19 | 27 | 35 | 42 | 51 | 58 | 65
308 | 8 | 7 | 7 | 8 | 7 | 9 | 9 | 7 | 8 | 15 | 22 | 30 | 37 | 46 | 55 | 62
309 | 12 | 8 | 11 | 7 | 11 | 8 | 7 | 7 | 12 | 20 | 31 | 38 | 49 | 57 | 64 | 71
310 | 8 | 8 | 8 | 11 | 11 | 11 | 7 | 7 | 8 | 16 | 24 | 35 | 46 | 57 | 64 | 71
311 | 9 | 7 | 7 | 12 | 7 | 8 | 11 | 7 | 9 | 16 | 23 | 35 | 42 | 50 | 61 | 68
312 | 9 | 7 | 7 | 11 | 8 | 8 | 8 | 9 | 9 | 16 | 23 | 34 | 42 | 50 | 58 | 67
313 | 8 | 7 | 8 | 9 | 12 | 11 | 7 | 11 | 8 | 15 | 23 | 32 | 44 | 55 | 62 | 73
314 | 9 | 8 | 7 | 12 | 7 | 8 | 11 | 8 | 9 | 17 | 24 | 36 | 43 | 51 | 62 | 70
315 | 11 | 8 | 8 | 8 | 7 | 11 | 11 | 12 | 11 | 19 | 27 | 35 | 42 | 53 | 64 | 76
316 | 8 | 8 | 8 | 7 | 11 | 8 | 11 | 9 | 8 | 16 | 24 | 31 | 42 | 50 | 61 | 70
317 | 8 | 11 | 11 | 12 | 8 | 11 | 8 | 11 | 8 | 19 | 30 | 42 | 50 | 61 | 69 | 80
318 | 11 | 9 | 12 | 7 | 11 | 12 | 12 | 7 | 11 | 20 | 32 | 39 | 50 | 62 | 74 | 81
319 | 7 | 7 | 12 | 11 | 11 | 8 | 8 | 11 | 7 | 14 | 26 | 37 | 48 | 56 | 64 | 75
320 | 7 | 11 | 8 | 9 | 8 | 8 | 8 | 9 | 7 | 18 | 26 | 35 | 43 | 51 | 59 | 68
321 | 7 | 8 | 7 | 12 | 9 | 8 | 7 | 12 | 7 | 15 | 22 | 34 | 43 | 51 | 58 | 70
322 | 8 | 8 | 12 | 9 | 8 | 7 | 8 | 8 | 8 | 16 | 28 | 37 | 45 | 52 | 60 | 68
323 | 9 | 8 | 9 | 9 | 12 | 9 | 11 | 8 | 9 | 17 | 26 | 35 | 47 | 56 | 67 | 75
324 | 11 | 8 | 8 | 11 | 8 | 11 | 9 | 9 | 11 | 19 | 27 | 38 | 46 | 57 | 66 | 75
325 | 9 | 11 | 12 | 7 | 9 | 11 | 9 | 8 | 9 | 20 | 32 | 39 | 48 | 59 | 68 | 76
326 | 11 | 7 | 8 | 11 | 9 | 8 | 7 | 11 | 11 | 18 | 26 | 37 | 46 | 54 | 61 | 72
327 | 12 | 9 | 7 | 11 | 9 | 7 | 8 | 7 | 12 | 21 | 28 | 39 | 48 | 55 | 63 | 70
328 | 7 | 9 | 8 | 7 | 9 | 9 | 11 | 7 | 7 | 16 | 24 | 31 | 40 | 49 | 60 | 67
329 | 9 | 12 | 8 | 8 | 9 | 9 | 9 | 12 | 9 | 21 | 29 | 37 | 46 | 55 | 64 | 76
330 | 8 | 8 | 7 | 9 | 7 | 8 | 8 | 8 | 8 | 16 | 23 | 32 | 39 | 47 | 55 | 63
331 | 11 | 8 | 12 | 8 | 7 | 7 | 9 | 8 | 11 | 19 | 31 | 39 | 46 | 53 | 62 | 70
332 | 12 | 12 | 8 | 9 | 7 | 9 | 7 | 11 | 12 | 24 | 32 | 41 | 48 | 57 | 64 | 75
333 | 11 | 9 | 8 | 8 | 8 | 8 | 11 | 8 | 11 | 20 | 28 | 36 | 44 | 52 | 63 | 71
334 | 11 | 8 | 7 | 7 | 9 | 7 | 8 | 12 | 11 | 19 | 26 | 33 | 42 | 49 | 57 | 69
335 | 7 | 12 | 7 | 11 | 8 | 7 | 8 | 8 | 7 | 19 | 26 | 37 | 45 | 52 | 60 | 68
336 | 12 | 11 | 8 | 11 | 7 | 7 | 12 | 7 | 12 | 23 | 31 | 42 | 49 | 56 | 68 | 75
337 | 9 | 12 | 7 | 8 | 9 | 9 | 7 | 8 | 9 | 21 | 28 | 36 | 45 | 54 | 61 | 69
338 | 7 | 9 | 9 | 7 | 8 | 11 | 8 | 8 | 7 | 16 | 25 | 32 | 40 | 51 | 59 | 67
339 | 9 | 9 | 7 | 9 | 8 | 12 | 8 | 8 | 9 | 18 | 25 | 34 | 42 | 54 | 62 | 70
340 | 8 | 7 | 12 | 8 | 9 | 9 | 8 | 8 | 8 | 15 | 27 | 35 | 44 | 53 | 61 | 69
341 | 9 | 9 | 8 | 9 | 12 | 11 | 8 | 9 | 9 | 18 | 26 | 35 | 47 | 58 | 66 | 75
342 | 9 | 7 | 8 | 8 | 9 | 8 | 7 | 11 | 9 | 16 | 24 | 32 | 41 | 49 | 56 | 67
343 | 8 | 7 | 12 | 7 | 8 | 9 | 8 | 9 | 8 | 15 | 27 | 34 | 42 | 51 | 59 | 68
344 | 9 | 9 | 9 | 8 | 8 | 9 | 7 | 8 | 9 | 18 | 27 | 35 | 43 | 52 | 59 | 67
345 | 7 | 11 | 12 | 11 | 7 | 7 | 11 | 8 | 7 | 18 | 30 | 41 | 48 | 55 | 66 | 74
346 | 12 | 8 | 11 | 7 | 11 | 12 | 7 | 9 | 12 | 20 | 31 | 38 | 49 | 61 | 68 | 77
347 | 11 | 8 | 7 | 8 | 11 | 8 | 11 | 8 | 11 | 19 | 26 | 34 | 45 | 53 | 64 | 72
348 | 12 | 7 | 9 | 8 | 8 | 12 | 8 | 9 | 12 | 19 | 28 | 36 | 44 | 56 | 64 | 73
349 | 8 | 12 | 9 | 8 | 11 | 8 | 7 | 11 | 8 | 20 | 29 | 37 | 48 | 56 | 63 | 74
350 | 9 | 12 | 9 | 12 | 11 | 11 | 7 | 11 | 9 | 21 | 30 | 42 | 53 | 64 | 71 | 82
351 | 7 | 11 | 8 | 11 | 7 | 12 | 11 | 8 | 7 | 18 | 26 | 37 | 44 | 56 | 67 | 75
352 | 9 | 9 | 11 | 8 | 12 | 11 | 7 | 7 | 9 | 18 | 29 | 37 | 49 | 60 | 67 | 74
353 | 8 | 9 | 8 | 11 | 9 | 12 | 11 | 7 | 8 | 17 | 25 | 36 | 45 | 57 | 68 | 75
354 | 9 | 12 | 11 | 8 | 11 | 7 | 8 | 11 | 9 | 21 | 32 | 40 | 51 | 58 | 66 | 77
355 | 11 | 8 | 7 | 11 | 9 | 9 | 9 | 8 | 11 | 19 | 26 | 37 | 46 | 55 | 64 | 72
356 | 9 | 7 | 11 | 9 | 7 | 8 | 7 | 7 | 9 | 16 | 27 | 36 | 43 | 51 | 58 | 65
357 | 8 | 11 | 8 | 7 | 8 | 8 | 11 | 9 | 8 | 19 | 27 | 34 | 42 | 50 | 61 | 70
358 | 12 | 8 | 8 | 12 | 8 | 12 | 9 | 8 | 12 | 20 | 28 | 40 | 48 | 60 | 69 | 77
359 | 8 | 12 | 12 | 12 | 8 | 7 | 11 | 8 | 8 | 20 | 32 | 44 | 52 | 59 | 70 | 78
360 | 12 | 9 | 9 | 11 | 8 | 8 | 9 | 12 | 12 | 21 | 30 | 41 | 49 | 57 | 66 | 78
361 | 11 | 11 | 7 | 7 | 9 | 11 | 8 | 8 | 11 | 22 | 29 | 36 | 45 | 56 | 64 | 72
362 | 7 | 9 | 7 | 8 | 11 | 8 | 11 | 11 | 7 | 16 | 23 | 31 | 42 | 50 | 61 | 72
363 | 7 | 9 | 9 | 7 | 7 | 8 | 11 | 8 | 7 | 16 | 25 | 32 | 39 | 47 | 58 | 66
364 | 11 | 8 | 9 | 7 | 11 | 8 | 11 | 8 | 11 | 19 | 28 | 35 | 46 | 54 | 65 | 73
365 | 8 | 9 | 8 | 12 | 12 | 7 | 12 | 11 | 8 | 17 | 25 | 37 | 49 | 56 | 68 | 79
366 | 8 | 8 | 11 | 8 | 7 | 9 | 11 | 9 | 8 | 16 | 27 | 35 | 42 | 51 | 62 | 71
367 | 11 | 8 | 8 | 8 | 7 | 11 | 8 | 8 | 11 | 19 | 27 | 35 | 42 | 53 | 61 | 69
368 | 8 | 7 | 11 | 7 | 11 | 8 | 7 | 8 | 8 | 15 | 26 | 33 | 44 | 52 | 59 | 67
369 | 8 | 9 | 7 | 7 | 8 | 7 | 12 | 11 | 8 | 17 | 24 | 31 | 39 | 46 | 58 | 69
370 | 8 | 11 | 8 | 7 | 9 | 11 | 9 | 8 | 8 | 19 | 27 | 34 | 43 | 54 | 63 | 71
371 | 12 | 8 | 7 | 11 | 8 | 8 | 8 | 8 | 12 | 20 | 27 | 38 | 46 | 54 | 62 | 70
372 | 8 | 9 | 11 | 11 | 12 | 7 | 7 | 12 | 8 | 17 | 28 | 39 | 51 | 58 | 65 | 77
373 | 12 | 7 | 9 | 12 | 7 | 8 | 9 | 7 | 12 | 19 | 28 | 40 | 47 | 55 | 64 | 71
374 | 11 | 11 | 9 | 9 | 9 | 7 | 11 | 9 | 11 | 22 | 31 | 40 | 49 | 56 | 67 | 76
375 | 8 | 9 | 8 | 11 | 11 | 7 | 7 | 12 | 8 | 17 | 25 | 36 | 47 | 54 | 61 | 73
376 | 9 | 12 | 9 | 8 | 12 | 8 | 12 | 7 | 9 | 21 | 30 | 38 | 50 | 58 | 70 | 77
377 | 9 | 7 | 8 | 8 | 7 | 7 | 9 | 7 | 9 | 16 | 24 | 32 | 39 | 46 | 55 | 62
378 | 7 | 7 | 9 | 7 | 11 | 11 | 8 | 12 | 7 | 14 | 23 | 30 | 41 | 52 | 60 | 72
379 | 7 | 11 | 7 | 9 | 11 | 11 | 9 | 11 | 7 | 18 | 25 | 34 | 45 | 56 | 65 | 76
380 | 8 | 9 | 8 | 11 | 12 | 8 | 11 | 7 | 8 | 17 | 25 | 36 | 48 | 56 | 67 | 74
381 | 9 | 9 | 12 | 7 | 8 | 11 | 7 | 9 | 9 | 18 | 30 | 37 | 45 | 56 | 63 | 72
382 | 8 | 8 | 7 | 11 | 8 | 9 | 12 | 7 | 8 | 16 | 23 | 34 | 42 | 51 | 63 | 70
383 | 11 | 7 | 9 | 9 | 11 | 8 | 8 | 11 | 11 | 18 | 27 | 36 | 47 | 55 | 63 | 74
384 | 11 | 7 | 7 | 11 | 11 | 9 | 11 | 7 | 11 | 18 | 25 | 36 | 47 | 56 | 67 | 74
385 | 11 | 7 | 7 | 9 | 7 | 7 | 8 | 12 | 11 | 18 | 25 | 34 | 41 | 48 | 56 | 68
386 | 8 | 11 | 11 | 9 | 7 | 11 | 9 | 8 | 8 | 19 | 30 | 39 | 46 | 57 | 66 | 74
387 | 8 | 8 | 8 | 12 | 8 | 12 | 9 | 11 | 8 | 16 | 24 | 36 | 44 | 56 | 65 | 76
388 | 8 | 8 | 8 | 9 | 9 | 8 | 7 | 8 | 8 | 16 | 24 | 33 | 42 | 50 | 57 | 65
389 | 8 | 8 | 8 | 7 | 12 | 7 | 9 | 11 | 8 | 16 | 24 | 31 | 43 | 50 | 59 | 70
390 | 9 | 9 | 7 | 11 | 9 | 7 | 9 | 7 | 9 | 18 | 25 | 36 | 45 | 52 | 61 | 68
391 | 8 | 8 | 9 | 8 | 9 | 11 | 8 | 7 | 8 | 16 | 25 | 33 | 42 | 53 | 61 | 68
392 | 8 | 11 | 7 | 11 | 11 | 11 | 8 | 7 | 8 | 19 | 26 | 37 | 48 | 59 | 67 | 74
393 | 7 | 11 | 9 | 8 | 8 | 9 | 11 | 8 | 7 | 18 | 27 | 35 | 43 | 52 | 63 | 71
394 | 8 | 9 | 8 | 8 | 7 | 8 | 11 | 9 | 8 | 17 | 25 | 33 | 40 | 48 | 59 | 68
395 | 9 | 7 | 9 | 12 | 9 | 11 | 7 | 8 | 9 | 16 | 25 | 37 | 46 | 57 | 64 | 72
396 | 9 | 7 | 7 | 9 | 7 | 11 | 8 | 12 | 9 | 16 | 23 | 32 | 39 | 50 | 58 | 70
397 | 8 | 8 | 12 | 8 | 7 | 11 | 9 | 7 | 8 | 16 | 28 | 36 | 43 | 54 | 63 | 70
398 | 8 | 7 | 7 | 9 | 7 | 9 | 7 | 11 | 8 | 15 | 22 | 31 | 38 | 47 | 54 | 65
399 | 12 | 11 | 12 | 9 | 7 | 11 | 8 | 7 | 12 | 23 | 35 | 44 | 51 | 62 | 70 | 77
400 | 7 | 7 | 8 | 7 | 8 | 8 | 11 | 7 | 7 | 14 | 22 | 29 | 37 | 45 | 56 | 63
401 | 8 | 8 | 9 | 7 | 8 | 7 | 9 | 9 | 8 | 16 | 25 | 32 | 40 | 47 | 56 | 65
402 | 7 | 9 | 7 | 8 | 11 | 9 | 11 | 8 | 7 | 16 | 23 | 31 | 42 | 51 | 62 | 70
403 | 7 | 8 | 7 | 8 | 8 | 8 | 12 | 8 | 7 | 15 | 22 | 30 | 38 | 46 | 58 | 66
404 | 12 | 8 | 7 | 8 | 11 | 8 | 8 | 8 | 12 | 20 | 27 | 35 | 46 | 54 | 62 | 70
405 | 8 | 8 | 8 | 7 | 8 | 7 | 7 | 11 | 8 | 16 | 24 | 31 | 39 | 46 | 53 | 64
406 | 9 | 8 | 8 | 8 | 12 | 9 | 8 | 8 | 9 | 17 | 25 | 33 | 45 | 54 | 62 | 70
407 | 9 | 8 | 12 | 7 | 12 | 9 | 8 | 8 | 9 | 17 | 29 | 36 | 48 | 57 | 65 | 73
408 | 11 | 12 | 8 | 8 | 9 | 7 | 8 | 12 | 11 | 23 | 31 | 39 | 48 | 55 | 63 | 75
409 | 8 | 9 | 11 | 8 | 7 | 11 | 9 | 8 | 8 | 17 | 28 | 36 | 43 | 54 | 63 | 71
410 | 8 | 8 | 12 | 11 | 8 | 12 | 7 | 7 | 8 | 16 | 28 | 39 | 47 | 59 | 66 | 73
411 | 8 | 9 | 9 | 8 | 8 | 12 | 9 | 9 | 8 | 17 | 26 | 34 | 42 | 54 | 63 | 72
412 | 9 | 12 | 12 | 7 | 12 | 11 | 8 | 12 | 9 | 21 | 33 | 40 | 52 | 63 | 71 | 83
413 | 8 | 8 | 11 | 11 | 11 | 9 | 11 | 11 | 8 | 16 | 27 | 38 | 49 | 58 | 69 | 80
414 | 9 | 12 | 8 | 8 | 9 | 12 | 8 | 7 | 9 | 21 | 29 | 37 | 46 | 58 | 66 | 73
415 | 9 | 8 | 11 | 9 | 11 | 12 | 8 | 7 | 9 | 17 | 28 | 37 | 48 | 60 | 68 | 75
416 | 11 | 11 | 8 | 8 | 11 | 9 | 11 | 12 | 11 | 22 | 30 | 38 | 49 | 58 | 69 | 81
417 | 7 | 8 | 11 | 7 | 8 | 8 | 12 | 7 | 7 | 15 | 26 | 33 | 41 | 49 | 61 | 68
418 | 9 | 12 | 7 | 11 | 7 | 7 | 8 | 11 | 9 | 21 | 28 | 39 | 46 | 53 | 61 | 72
419 | 9 | 9 | 12 | 9 | 7 | 7 | 11 | 12 | 9 | 18 | 30 | 39 | 46 | 53 | 64 | 76
420 | 8 | 9 | 12 | 11 | 9 | 8 | 8 | 11 | 8 | 17 | 29 | 40 | 49 | 57 | 65 | 76
421 | 8 | 11 | 9 | 8 | 8 | 11 | 7 | 7 | 8 | 19 | 28 | 36 | 44 | 55 | 62 | 69
422 | 9 | 12 | 7 | 9 | 11 | 9 | 7 | 12 | 9 | 21 | 28 | 37 | 48 | 57 | 64 | 76
423 | 8 | 11 | 7 | 11 | 8 | 11 | 7 | 8 | 8 | 19 | 26 | 37 | 45 | 56 | 63 | 71
424 | 8 | 12 | 7 | 8 | 7 | 8 | 8 | 8 | 8 | 20 | 27 | 35 | 42 | 50 | 58 | 66
425 | 7 | 12 | 8 | 7 | 11 | 11 | 7 | 7 | 7 | 19 | 27 | 34 | 45 | 56 | 63 | 70
426 | 9 | 11 | 7 | 11 | 12 | 9 | 7 | 8 | 9 | 20 | 27 | 38 | 50 | 59 | 66 | 74
427 | 11 | 7 | 8 | 7 | 9 | 7 | 7 | 7 | 11 | 18 | 26 | 33 | 42 | 49 | 56 | 63
428 | 9 | 11 | 7 | 8 | 12 | 8 | 7 | 7 | 9 | 20 | 27 | 35 | 47 | 55 | 62 | 69
429 | 7 | 8 | 8 | 8 | 8 | 9 | 11 | 9 | 7 | 15 | 23 | 31 | 39 | 48 | 59 | 68
430 | 12 | 12 | 7 | 8 | 7 | 12 | 7 | 9 | 12 | 24 | 31 | 39 | 46 | 58 | 65 | 74
431 | 8 | 8 | 9 | 11 | 11 | 8 | 9 | 8 | 8 | 16 | 25 | 36 | 47 | 55 | 64 | 72
432 | 8 | 9 | 12 | 9 | 12 | 11 | 8 | 8 | 8 | 17 | 29 | 38 | 50 | 61 | 69 | 77
433 | 7 | 9 | 7 | 8 | 12 | 7 | 9 | 9 | 7 | 16 | 23 | 31 | 43 | 50 | 59 | 68
434 | 8 | 7 | 7 | 8 | 7 | 8 | 7 | 8 | 8 | 15 | 22 | 30 | 37 | 45 | 52 | 60
435 | 8 | 11 | 7 | 11 | 9 | 8 | 8 | 11 | 8 | 19 | 26 | 37 | 46 | 54 | 62 | 73
436 | 9 | 9 | 11 | 11 | 8 | 9 | 7 | 9 | 9 | 18 | 29 | 40 | 48 | 57 | 64 | 73
437 | 8 | 9 | 9 | 7 | 8 | 9 | 12 | 8 | 8 | 17 | 26 | 33 | 41 | 50 | 62 | 70
438 | 8 | 9 | 11 | 8 | 8 | 7 | 12 | 11 | 8 | 17 | 28 | 36 | 44 | 51 | 63 | 74
439 | 9 | 8 | 7 | 8 | 7 | 8 | 11 | 8 | 9 | 17 | 24 | 32 | 39 | 47 | 58 | 66
440 | 11 | 7 | 8 | 9 | 8 | 7 | 9 | 9 | 11 | 18 | 26 | 35 | 43 | 50 | 59 | 68
441 | 11 | 7 | 11 | 11 | 7 | 11 | 12 | 8 | 11 | 18 | 29 | 40 | 47 | 58 | 70 | 78
442 | 7 | 11 | 7 | 12 | 7 | 11 | 9 | 8 | 7 | 18 | 25 | 37 | 44 | 55 | 64 | 72
443 | 7 | 9 | 8 | 9 | 8 | 8 | 8 | 8 | 7 | 16 | 24 | 33 | 41 | 49 | 57 | 65
444 | 7 | 12 | 12 | 11 | 11 | 8 | 7 | 7 | 7 | 19 | 31 | 42 | 53 | 61 | 68 | 75
445 | 7 | 8 | 9 | 8 | 8 | 9 | 9 | 9 | 7 | 15 | 24 | 32 | 40 | 49 | 58 | 67
446 | 8 | 11 | 11 | 8 | 8 | 9 | 7 | 9 | 8 | 19 | 30 | 38 | 46 | 55 | 62 | 71
447 | 11 | 9 | 11 | 7 | 11 | 8 | 7 | 8 | 11 | 20 | 31 | 38 | 49 | 57 | 64 | 72
448 | 12 | 8 | 9 | 8 | 9 | 11 | 7 | 8 | 12 | 20 | 29 | 37 | 46 | 57 | 64 | 72
449 | 9 | 11 | 8 | 8 | 7 | 9 | 11 | 9 | 9 | 20 | 28 | 36 | 43 | 52 | 63 | 72
450 | 12 | 11 | 8 | 8 | 12 | 7 | 8 | 12 | 12 | 23 | 31 | 39 | 51 | 58 | 66 | 78
451 | 9 | 7 | 9 | 9 | 11 | 11 | 7 | 8 | 9 | 16 | 25 | 34 | 45 | 56 | 63 | 71
452 | 8 | 7 | 11 | 9 | 9 | 9 | 11 | 11 | 8 | 15 | 26 | 35 | 44 | 53 | 64 | 75
453 | 11 | 9 | 8 | 8 | 9 | 11 | 7 | 11 | 11 | 20 | 28 | 36 | 45 | 56 | 63 | 74
454 | 8 | 8 | 9 | 11 | 8 | 9 | 9 | 8 | 8 | 16 | 25 | 36 | 44 | 53 | 62 | 70
455 | 7 | 9 | 11 | 8 | 9 | 11 | 8 | 7 | 7 | 16 | 27 | 35 | 44 | 55 | 63 | 70
456 | 8 | 8 | 8 | 7 | 7 | 11 | 12 | 7 | 8 | 16 | 24 | 31 | 38 | 49 | 61 | 68
457 | 7 | 11 | 8 | 8 | 9 | 9 | 8 | 7 | 7 | 18 | 26 | 34 | 43 | 52 | 60 | 67
458 | 8 | 7 | 11 | 11 | 11 | 8 | 11 | 8 | 8 | 15 | 26 | 37 | 48 | 56 | 67 | 75
459 | 8 | 7 | 7 | 8 | 8 | 8 | 12 | 7 | 8 | 15 | 22 | 30 | 38 | 46 | 58 | 65
460 | 11 | 11 | 8 | 11 | 11 | 9 | 12 | 7 | 11 | 22 | 30 | 41 | 52 | 61 | 73 | 80
461 | 7 | 7 | 9 | 8 | 8 | 8 | 11 | 9 | 7 | 14 | 23 | 31 | 39 | 47 | 58 | 67
462 | 7 | 7 | 11 | 8 | 8 | 11 | 9 | 9 | 7 | 14 | 25 | 33 | 41 | 52 | 61 | 70
463 | 7 | 12 | 7 | 8 | 9 | 9 | 7 | 9 | 7 | 19 | 26 | 34 | 43 | 52 | 59 | 68
464 | 7 | 12 | 8 | 9 | 12 | 9 | 9 | 8 | 7 | 19 | 27 | 36 | 48 | 57 | 66 | 74
465 | 11 | 8 | 11 | 8 | 7 | 7 | 11 | 8 | 11 | 19 | 30 | 38 | 45 | 52 | 63 | 71
466 | 11 | 9 | 7 | 11 | 11 | 8 | 12 | 7 | 11 | 20 | 27 | 38 | 49 | 57 | 69 | 76
467 | 7 | 7 | 7 | 7 | 8 | 9 | 8 | 9 | 7 | 14 | 21 | 28 | 36 | 45 | 53 | 62
468 | 11 | 8 | 12 | 9 | 11 | 7 | 11 | 8 | 11 | 19 | 31 | 40 | 51 | 58 | 69 | 77
469 | 8 | 9 | 7 | 7 | 7 | 7 | 9 | 8 | 8 | 17 | 24 | 31 | 38 | 45 | 54 | 62
470 | 11 | 8 | 9 | 11 | 7 | 8 | 8 | 11 | 11 | 19 | 28 | 39 | 46 | 54 | 62 | 73
471 | 11 | 8 | 8 | 7 | 11 | 9 | 8 | 8 | 11 | 19 | 27 | 34 | 45 | 54 | 62 | 70
472 | 9 | 8 | 8 | 11 | 11 | 8 | 7 | 7 | 9 | 17 | 25 | 36 | 47 | 55 | 62 | 69
473 | 11 | 12 | 7 | 8 | 8 | 7 | 7 | 12 | 11 | 23 | 30 | 38 | 46 | 53 | 60 | 72
474 | 9 | 7 | 7 | 8 | 8 | 7 | 9 | 7 | 9 | 16 | 23 | 31 | 39 | 46 | 55 | 62
475 | 8 | 11 | 9 | 8 | 7 | 9 | 9 | 7 | 8 | 19 | 28 | 36 | 43 | 52 | 61 | 68
476 | 9 | 11 | 7 | 11 | 7 | 8 | 8 | 8 | 9 | 20 | 27 | 38 | 45 | 53 | 61 | 69
477 | 8 | 11 | 9 | 8 | 7 | 8 | 11 | 8 | 8 | 19 | 28 | 36 | 43 | 51 | 62 | 70
478 | 7 | 12 | 11 | 9 | 8 | 7 | 9 | 7 | 7 | 19 | 30 | 39 | 47 | 54 | 63 | 70
479 | 11 | 9 | 7 | 8 | 8 | 11 | 9 | 11 | 11 | 20 | 27 | 35 | 43 | 54 | 63 | 74
480 | 8 | 8 | 9 | 11 | 8 | 8 | 9 | 7 | 8 | 16 | 25 | 36 | 44 | 52 | 61 | 68
481 | 9 | 8 | 11 | 8 | 7 | 9 | 11 | 9 | 9 | 17 | 28 | 36 | 43 | 52 | 63 | 72
482 | 8 | 8 | 8 | 9 | 8 | 11 | 7 | 11 | 8 | 16 | 24 | 33 | 41 | 52 | 59 | 70
483 | 8 | 8 | 7 | 8 | 7 | 9 | 8 | 12 | 8 | 16 | 23 | 31 | 38 | 47 | 55 | 67
484 | 9 | 8 | 9 | 9 | 8 | 8 | 8 | 7 | 9 | 17 | 26 | 35 | 43 | 51 | 59 | 66
485 | 11 | 9 | 8 | 9 | 11 | 7 | 9 | 8 | 11 | 20 | 28 | 37 | 48 | 55 | 64 | 72
486 | 9 | 11 | 7 | 11 | 11 | 8 | 11 | 9 | 9 | 20 | 27 | 38 | 49 | 57 | 68 | 77
487 | 8 | 8 | 8 | 8 | 8 | 9 | 8 | 11 | 8 | 16 | 24 | 32 | 40 | 49 | 57 | 68
488 | 11 | 8 | 9 | 8 | 8 | 8 | 7 | 9 | 11 | 19 | 28 | 36 | 44 | 52 | 59 | 68
489 | 11 | 9 | 9 | 11 | 8 | 9 | 12 | 7 | 11 | 20 | 29 | 40 | 48 | 57 | 69 | 76
490 | 9 | 8 | 7 | 11 | 12 | 8 | 11 | 11 | 9 | 17 | 24 | 35 | 47 | 55 | 66 | 77
491 | 8 | 7 | 8 | 7 | 11 | 8 | 8 | 8 | 8 | 15 | 23 | 30 | 41 | 49 | 57 | 65
492 | 7 | 9 | 7 | 7 | 9 | 8 | 7 | 8 | 7 | 16 | 23 | 30 | 39 | 47 | 54 | 62
493 | 8 | 12 | 7 | 7 | 9 | 11 | 7 | 8 | 8 | 20 | 27 | 34 | 43 | 54 | 61 | 69
494 | 8 | 11 | 11 | 11 | 11 | 8 | 9 | 8 | 8 | 19 | 30 | 41 | 52 | 60 | 69 | 77
495 | 12 | 8 | 9 | 8 | 9 | 8 | 9 | 8 | 12 | 20 | 29 | 37 | 46 | 54 | 63 | 71
496 | 7 | 8 | 12 | 8 | 8 | 9 | 7 | 11 | 7 | 15 | 27 | 35 | 43 | 52 | 59 | 70
497 | 12 | 8 | 11 | 8 | 8 | 9 | 9 | 11 | 12 | 20 | 31 | 39 | 47 | 56 | 65 | 76
498 | 8 | 7 | 9 | 8 | 8 | 7 | 8 | 7 | 8 | 15 | 24 | 32 | 40 | 47 | 55 | 62
499 | 8 | 12 | 7 | 7 | 7 | 8 | 8 | 9 | 8 | 20 | 27 | 34 | 41 | 49 | 57 | 66
500 | 8 | 9 | 7 | 8 | 7 | 11 | 8 | 7 | 8 | 17 | 24 | 32 | 39 | 50 | 58 | 65

## Jira_Data
Issue key | Summary | Issue Type | Status | Story Points | Sprint Committed | Created | Started | Resolved | Cycle Time (days) | Lead Time (days)
DEMO-101 | Add role permissions to mobile app | Story | Done | 2 | Sprint 1 | 2026-02-07 | 2026-03-04 | 2026-03-10 | 6 | 31
DEMO-102 | Update API documentation | Task | Done | 2 | Sprint 1 | 2026-02-08 | 2026-03-09 | 2026-03-17 | 8 | 37
DEMO-103 | Update CI pipeline config | Task | Done | 2 | Sprint 1 | 2026-02-10 | 2026-03-06 | 2026-03-10 | 4 | 28
DEMO-104 | Update database indices | Task | Done | 5 | Sprint 1 | 2026-02-12 | 2026-03-02 | 2026-03-09 | 7 | 25
DEMO-105 | Add search suggestions to mobile app | Story | Done | 1 | Sprint 2 | 2026-02-21 | 2026-03-17 | 2026-03-20 | 3 | 27
DEMO-106 | Add audit log to reporting module | Story | Done | 1 | Sprint 1 | 2026-02-22 | 2026-03-03 | 2026-03-04 | 1 | 10
DEMO-107 | Add audit log to mobile app | Story | Done | 3 | Sprint 2 | 2026-02-22 | 2026-03-19 | 2026-03-27 | 8 | 33
DEMO-108 | Fix missing validation in customer portal | Bug | Done | 1 | Sprint 1 | 2026-02-23 | 2026-03-10 | 2026-03-16 | 6 | 21
DEMO-109 | Fix broken pagination in reporting module | Bug | Done | 1 | Sprint 1 | 2026-02-26 | 2026-03-04 | 2026-03-09 | 5 | 11
DEMO-110 | Fix missing validation in customer portal | Bug | Done | 1 | Sprint 2 | 2026-02-26 | 2026-03-23 | 2026-03-26 | 3 | 28
DEMO-111 | Fix timeout on load in checkout | Bug | Done | 2 | Sprint 1 | 2026-02-27 | 2026-03-09 | 2026-03-12 | 3 | 13
DEMO-112 | Add password reset flow to admin console | Story | Done | 1 | Sprint 2 | 2026-02-27 | 2026-03-18 | 2026-03-20 | 2 | 21
DEMO-113 | Fix timeout on load in checkout | Bug | Done | 3 | Sprint 1 | 2026-02-28 | 2026-03-09 | 2026-03-11 | 2 | 11
DEMO-114 | Fix layout glitch on mobile in reporting module | Bug | Done | 1 | Sprint 2 | 2026-02-28 | 2026-03-23 | 2026-04-02 | 10 | 33
DEMO-115 | Fix broken pagination in reporting module | Bug | Done | 1 | Sprint 1 | 2026-03-01 | 2026-03-09 | 2026-03-13 | 4 | 12
DEMO-116 | Add profile avatars to customer portal | Story | Done | 3 | Sprint 2 | 2026-03-03 | 2026-03-23 | 2026-03-26 | 3 | 23
DEMO-117 | Update database indices | Task | Done | 5 | Sprint 2 | 2026-03-03 | 2026-03-24 | 2026-04-01 | 8 | 29
DEMO-118 | Fix layout glitch on mobile in mobile app | Bug | Done | 1 | Sprint 2 | 2026-03-05 | 2026-03-24 | 2026-03-26 | 2 | 21
DEMO-119 | Update API documentation | Task | Done | 2 | Sprint 3 | 2026-03-05 | 2026-04-02 | 2026-04-06 | 4 | 32
DEMO-120 | Update database indices | Task | Done | 3 | Sprint 3 | 2026-03-08 | 2026-03-31 | 2026-04-03 | 3 | 26
DEMO-121 | Add audit log to customer portal | Story | Done | 3 | Sprint 2 | 2026-03-10 | 2026-03-23 | 2026-03-26 | 3 | 16
DEMO-122 | Add password reset flow to admin console | Story | Done | 1 | Sprint 3 | 2026-03-10 | 2026-04-01 | 2026-04-03 | 2 | 24
DEMO-123 | Add SSO login to checkout | Story | Done | 1 | Sprint 2 | 2026-03-11 | 2026-03-23 | 2026-03-25 | 2 | 14
DEMO-124 | Add profile avatars to customer portal | Story | Done | 1 | Sprint 2 | 2026-03-13 | 2026-03-16 | 2026-03-19 | 3 | 6
DEMO-125 | Fix missing validation in mobile app | Bug | Done | 1 | Sprint 3 | 2026-03-13 | 2026-03-31 | 2026-04-13 | 13 | 31
DEMO-126 | Update API documentation | Task | Done | 3 | Sprint 3 | 2026-03-14 | 2026-04-07 | 2026-04-20 | 13 | 37
DEMO-127 | Fix broken pagination in mobile app | Bug | Done | 1 | Sprint 3 | 2026-03-14 | 2026-04-02 | 2026-04-06 | 4 | 23
DEMO-128 | Add export to CSV to customer portal | Story | Done | 5 | Sprint 3 | 2026-03-15 | 2026-04-06 | 2026-04-10 | 4 | 26
DEMO-129 | Add audit log to admin console | Story | Done | 3 | Sprint 3 | 2026-03-15 | 2026-04-06 | 2026-04-08 | 2 | 24
DEMO-130 | Add dark mode to reporting module | Story | Done | 1 | Sprint 4 | 2026-03-21 | 2026-04-15 | 2026-04-21 | 6 | 31
DEMO-131 | Update test data set | Task | Done | 2 | Sprint 3 | 2026-03-25 | 2026-04-07 | 2026-04-15 | 8 | 21
DEMO-132 | Update CI pipeline config | Task | Done | 2 | Sprint 4 | 2026-03-26 | 2026-04-14 | 2026-04-16 | 2 | 21
DEMO-133 | Update database indices | Task | Done | 2 | Sprint 4 | 2026-03-27 | 2026-04-20 | 2026-04-22 | 2 | 26
DEMO-134 | Add export to CSV to reporting module | Story | Done | 5 | Sprint 4 | 2026-03-28 | 2026-04-15 | 2026-04-22 | 7 | 25
DEMO-135 | Add dark mode to mobile app | Story | Done | 1 | Sprint 4 | 2026-04-02 | 2026-04-20 | 2026-04-27 | 7 | 25
DEMO-136 | Fix layout glitch on mobile in mobile app | Bug | Done | 1 | Sprint 4 | 2026-04-02 | 2026-04-20 | 2026-04-24 | 4 | 22
DEMO-137 | Update database indices | Task | Done | 2 | Sprint 4 | 2026-04-02 | 2026-04-13 | 2026-04-22 | 9 | 20
DEMO-138 | Add SSO login to customer portal | Story | Done | 2 | Sprint 4 | 2026-04-05 | 2026-04-14 | 2026-04-17 | 3 | 12
DEMO-139 | Add invoice download to checkout | Story | Done | 3 | Sprint 5 | 2026-04-05 | 2026-04-28 | 2026-04-30 | 2 | 25
DEMO-140 | Update test data set | Task | Done | 1 | Sprint 4 | 2026-04-07 | 2026-04-16 | 2026-04-20 | 4 | 13
DEMO-141 | Add dark mode to customer portal | Story | Done | 8 | Sprint 5 | 2026-04-10 | 2026-05-01 | 2026-05-05 | 4 | 25
DEMO-142 | Add API rate limiting to checkout | Story | Done | 3 | Sprint 5 | 2026-04-13 | 2026-04-29 | 2026-05-13 | 14 | 30
DEMO-143 | Add email notifications to customer portal | Story | Done | 5 | Sprint 5 | 2026-04-14 | 2026-05-01 | 2026-05-04 | 3 | 20
DEMO-144 | Fix missing validation in reporting module | Bug | Done | 3 | Sprint 5 | 2026-04-16 | 2026-04-30 | 2026-05-07 | 7 | 21
DEMO-145 | Add export to CSV to mobile app | Story | Done | 2 | Sprint 6 | 2026-04-16 | 2026-05-19 | 2026-05-22 | 3 | 36
DEMO-146 | Fix broken pagination in customer portal | Bug | Done | 1 | Sprint 5 | 2026-04-18 | 2026-04-28 | 2026-05-04 | 6 | 16
DEMO-147 | Add saved filters to mobile app | Story | Done | 8 | Sprint 6 | 2026-04-19 | 2026-05-19 | 2026-05-28 | 9 | 39
DEMO-148 | Fix incorrect totals in reporting module | Bug | Done | 2 | Sprint 6 | 2026-04-24 | 2026-05-18 | 2026-06-02 | 15 | 39
DEMO-149 | Add profile avatars to admin console | Story | Done | 1 | Sprint 6 | 2026-04-24 | 2026-05-13 | 2026-05-18 | 5 | 24
DEMO-150 | Fix missing validation in customer portal | Bug | Done | 2 | Sprint 5 | 2026-04-25 | 2026-04-29 | 2026-05-06 | 7 | 11
DEMO-151 | Update test data set | Task | Done | 2 | Sprint 5 | 2026-04-25 | 2026-05-01 | 2026-05-05 | 4 | 10
DEMO-152 | Update test data set | Task | Done | 2 | Sprint 6 | 2026-04-26 | 2026-05-15 | 2026-05-19 | 4 | 23
DEMO-153 | Fix broken pagination in admin console | Bug | Done | 3 | Sprint 7 | 2026-05-03 | 2026-06-01 | 2026-06-15 | 14 | 43
DEMO-154 | Add bulk edit to mobile app | Story | Done | 8 | Sprint 6 | 2026-05-04 | 2026-05-15 | 2026-05-21 | 6 | 17
DEMO-155 | Update monitoring alerts | Task | Done | 2 | Sprint 7 | 2026-05-05 | 2026-05-25 | 2026-05-28 | 3 | 23
DEMO-156 | Update API documentation | Task | Done | 1 | Sprint 7 | 2026-05-05 | 2026-05-29 | 2026-06-01 | 3 | 27
DEMO-157 | Update database indices | Task | Done | 3 | Sprint 6 | 2026-05-06 | 2026-05-18 | 2026-05-25 | 7 | 19
DEMO-158 | Add email notifications to customer portal | Story | Done | 1 | Sprint 6 | 2026-05-08 | 2026-05-14 | 2026-05-18 | 4 | 10
DEMO-159 | Update database indices | Task | Done | 3 | Sprint 6 | 2026-05-08 | 2026-05-14 | 2026-05-22 | 8 | 14
DEMO-160 | Add invoice download to admin console | Story | Done | 2 | Sprint 8 | 2026-05-14 | 2026-06-15 | 2026-06-18 | 3 | 35
DEMO-161 | Fix broken pagination in customer portal | Bug | Done | 2 | Sprint 8 | 2026-05-14 | 2026-06-11 | 2026-06-15 | 4 | 32
DEMO-162 | Update CI pipeline config | Task | Done | 2 | Sprint 7 | 2026-05-15 | 2026-06-01 | 2026-06-08 | 7 | 24
DEMO-163 | Update test data set | Task | Done | 2 | Sprint 7 | 2026-05-15 | 2026-05-28 | 2026-06-01 | 4 | 17
DEMO-164 | Fix missing validation in customer portal | Bug | Done | 2 | Sprint 7 | 2026-05-16 | 2026-06-01 | 2026-06-04 | 3 | 19
DEMO-165 | Add API rate limiting to admin console | Story | Done | 1 | Sprint 7 | 2026-05-16 | 2026-06-02 | 2026-06-04 | 2 | 19
DEMO-166 | Update monitoring alerts | Task | Done | 1 | Sprint 7 | 2026-05-17 | 2026-05-28 | 2026-06-01 | 4 | 15
DEMO-167 | Add export to CSV to reporting module | Story | Done | 5 | Sprint 7 | 2026-05-22 | 2026-06-02 | 2026-06-09 | 7 | 18
DEMO-168 | Update CI pipeline config | Task | Done | 5 | Sprint 8 | 2026-05-23 | 2026-06-12 | 2026-06-16 | 4 | 24
DEMO-169 | Update monitoring alerts | Task | Done | 2 | Sprint 8 | 2026-05-23 | 2026-06-08 | 2026-06-12 | 4 | 20
DEMO-170 | Add API rate limiting to checkout | Story | Done | 1 | Sprint 8 | 2026-05-26 | 2026-06-12 | 2026-06-15 | 3 | 20
DEMO-171 | Add audit log to customer portal | Story | Done | 8 | Sprint 8 | 2026-05-27 | 2026-06-09 | 2026-06-24 | 15 | 28
DEMO-172 | Add bulk edit to admin console | Story | Done | 3 | Sprint 8 | 2026-05-30 | 2026-06-09 | 2026-06-15 | 6 | 16
DEMO-173 | Add audit log to customer portal | Story | Done | 5 | Sprint 8 | 2026-06-01 | 2026-06-16 | 2026-07-06 | 20 | 35
DEMO-174 | Update test data set | Task | Done | 2 | Sprint 8 | 2026-06-01 | 2026-06-09 | 2026-06-15 | 6 | 14
DEMO-175 | Add role permissions to reporting module | Story | Done | 3 | Sprint 8 | 2026-06-03 | 2026-06-15 | 2026-06-18 | 3 | 15
DEMO-176 | Add audit log to customer portal | Story | To Do | 5 | Backlog | 2026-06-03
DEMO-177 | Add email notifications to reporting module | Story | To Do | 8 | Backlog | 2026-06-03
DEMO-178 | Add SSO login to mobile app | Story | Done | 8 | Sprint 9 | 2026-06-04 | 2026-06-25 | 2026-07-14 | 19 | 40
DEMO-179 | Add export to CSV to customer portal | Story | Done | 5 | Sprint 9 | 2026-06-05 | 2026-06-26 | 2026-07-02 | 6 | 27
DEMO-180 | Fix missing validation in mobile app | Bug | To Do | 1 | Backlog | 2026-06-06
DEMO-181 | Add dark mode to customer portal | Story | Done | 1 | Sprint 8 | 2026-06-07 | 2026-06-11 | 2026-06-15 | 4 | 8
DEMO-182 | Add role permissions to reporting module | Story | Done | 8 | Sprint 9 | 2026-06-07 | 2026-06-30 | 2026-07-06 | 6 | 29
DEMO-183 | Add audit log to mobile app | Story | Done | 1 | Sprint 9 | 2026-06-10 | 2026-06-29 | 2026-07-02 | 3 | 22
DEMO-184 | Add dark mode to customer portal | Story | To Do | 5 | Backlog | 2026-06-10
DEMO-185 | Add export to CSV to admin console | Story | Done | 2 | Sprint 10 | 2026-06-12 | 2026-07-14 | 2026-07-20 | 6 | 38
DEMO-186 | Add profile avatars to customer portal | Story | Done | 2 | Sprint 10 | 2026-06-12 | 2026-07-06 | 2026-07-10 | 4 | 28
DEMO-187 | Add dark mode to mobile app | Story | Done | 5 | Sprint 9 | 2026-06-18 | 2026-06-26 | 2026-06-29 | 3 | 11
DEMO-188 | Update API documentation | Task | To Do | 5 | Backlog | 2026-06-18
DEMO-189 | Fix incorrect totals in customer portal | Bug | Done | 1 | Sprint 9 | 2026-06-19 | 2026-06-29 | 2026-06-30 | 1 | 11
DEMO-190 | Add export to CSV to mobile app | Story | Done | 3 | Sprint 9 | 2026-06-19 | 2026-06-30 | 2026-07-09 | 9 | 20
DEMO-191 | Add usage report to reporting module | Story | Done | 2 | Sprint 9 | 2026-06-20 | 2026-06-24 | 2026-06-25 | 1 | 5
DEMO-192 | Add export to CSV to mobile app | Story | To Do | 3 | Backlog | 2026-06-20
DEMO-193 | Fix missing validation in customer portal | Bug | To Do | 1 | Backlog | 2026-06-20
DEMO-194 | Add export to CSV to checkout | Story | To Do | 1 | Backlog | 2026-06-20
DEMO-195 | Update CI pipeline config | Task | Done | 1 | Sprint 9 | 2026-06-21 | 2026-06-22 | 2026-06-24 | 2 | 3
DEMO-196 | Update API documentation | Task | Done | 2 | Sprint 10 | 2026-06-22 | 2026-07-08 | 2026-07-22 | 14 | 30
DEMO-197 | Add API rate limiting to customer portal | Story | Done | 3 | Sprint 10 | 2026-06-22 | 2026-07-10 | 2026-07-15 | 5 | 23
DEMO-198 | Add export to CSV to mobile app | Story | To Do | 5 | Backlog | 2026-06-23
DEMO-199 | Update API documentation | Task | Done | 3 | Sprint 10 | 2026-06-24 | 2026-07-13 | 2026-07-20 | 7 | 26
DEMO-200 | Fix missing validation in admin console | Bug | Done | 3 | Sprint 10 | 2026-06-25 | 2026-07-09 | 2026-07-22 | 13 | 27
DEMO-201 | Update CI pipeline config | Task | Done | 1 | Sprint 10 | 2026-06-27 | 2026-07-13 | 2026-07-15 | 2 | 18
DEMO-202 | Update monitoring alerts | Task | Done | 2 | Sprint 10 | 2026-06-30 | 2026-07-13 | 2026-07-23 | 10 | 23
DEMO-203 | Update CI pipeline config | Task | In Review | 1 | Sprint 11 | 2026-07-02 | 2026-07-21
DEMO-204 | Add bulk edit to mobile app | Story | To Do | 1 | Backlog | 2026-07-02
DEMO-205 | Add email notifications to reporting module | Story | Done | 5 | Sprint 10 | 2026-07-03 | 2026-07-10 | 2026-07-24 | 14 | 21
DEMO-206 | Fix missing validation in mobile app | Bug | Done | 1 | Sprint 10 | 2026-07-03 | 2026-07-13 | 2026-07-16 | 3 | 13
DEMO-207 | Add invoice download to reporting module | Story | Done | 1 | Sprint 10 | 2026-07-05 | 2026-07-13 | 2026-07-16 | 3 | 11
DEMO-208 | Add usage report to checkout | Story | To Do | 1 | Backlog | 2026-07-05
DEMO-209 | Update test data set | Task | To Do | 2 | Backlog | 2026-07-05
DEMO-210 | Add profile avatars to mobile app | Story | To Do | 5 | Backlog | 2026-07-05
DEMO-211 | Update CI pipeline config | Task | To Do | 1 | Sprint 11 | 2026-07-06
DEMO-212 | Fix timeout on load in mobile app | Bug | In Progress | 2 | Sprint 11 | 2026-07-09 | 2026-07-24
DEMO-213 | Add onboarding checklist to admin console | Story | To Do | 2 | Sprint 11 | 2026-07-09
DEMO-214 | Add audit log to reporting module | Story | In Progress | 3 | Sprint 11 | 2026-07-10 | 2026-07-24
DEMO-215 | Add email notifications to mobile app | Story | In Progress | 1 | Sprint 11 | 2026-07-10 | 2026-07-21
DEMO-216 | Add email notifications to admin console | Story | In Review | 3 | Sprint 11 | 2026-07-10 | 2026-07-20
DEMO-217 | Fix broken pagination in customer portal | Bug | In Review | 2 | Sprint 11 | 2026-07-10 | 2026-07-20
DEMO-218 | Add saved filters to mobile app | Story | In Progress | 5 | Sprint 11 | 2026-07-11 | 2026-07-22
DEMO-219 | Add profile avatars to checkout | Story | To Do | 1 | Sprint 11 | 2026-07-15
DEMO-220 | Fix timeout on load in checkout | Bug | To Do | 1 | Backlog | 2026-07-15